## Slide 1
Machine meeting 16.7.19 - UNILAC
  LEBT QQ beam pipe:
    A-pipe: welding finished, leak tested, okay,
    mounting of cooling jacket successful, but...
    test with backup tube done (8th – 10th July)
    test with unloaded magnet done (11th and 12th July)
  HSI RFQ:
    9 sections re-assembled
    now working on 10th section
    ...for setup for LLRF measurements
  Vacuum controls upgrade
    connecting of contactor controllers continued

## Slide 2
Machine meeting 2.7.19 - UNILAC
  Vacuum controls upgrade:
    LSB2: on schedule
      Equipping and connecting of new racks in progress
      connecting of contactor controllers continued
    LSB4: on schedule
      New racks in place
      Mounting of contactor controllers continued
  FoS:
    ready for UHV FAT -> next Monday together with VAC
    Cu cathode supports production proceeds well
    drift tube with quadrupole ordered