## Slide 1: Operations - 03.09.2019
Overall shutdown
  measurement result found a mould infestation of the LA16 air cooling system
    todays meeting with J. Dreger, N. Dausend, R. Becker, G. Schreiber, B. Schlitt, M. Hörr, J. Salvatore 
      health risk for workers on RF gallery + technical risk to contaminate RF amplifiers
      decision has been made, not to switch on LA16 until final result (expected next week)
    if further cleaning is necessary, several weeks of delay are expected
  nu further issues
Preparation Engineering-Run 2019
  beam study requests have been evaluated and discussed in machine meeting last week. The resulting priority list is updated in the table on operations web page: https://www.gsi.de/work/beschleunigerbetrieb/dokumente/gsi_beam_experiment_machine_development.htm
  first attempt to schedule A- und B- proposals within engineering run looks promising (request for comments)
  discussion on impact of delay?
Physics Run 2020
  official request has been send to management beginning this week, but decision can only be made after further clarification of the LA16 problematic