## Raw Schedule
2019-07-09
| August | [30 empty] | Stage | 8am - 8pm (Mo.-Fr.) | 8pm - 8am (Mo. - Fr.) + Weekend
| Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | RM1
Sources: HSI-UR | August Fr: RM2; August Mi: DELAY (Roof Renovation, LA16); August Mo: RM3 | RM2 | Abschluss Mechanik
[32 empty] | RM3 | Low Level HF IBN | 2
[32 empty] | RM4 | Vakuum IBN | - " -
[32 empty] | RM5 | Erste HF-Leistungs-IBN (Konditionierung) für Ar1+ | - " -
[32 empty] | RM6 | Strahlinbetriebnahme | - " -
[32 empty] | RM8 | Zweite HF-Leistungs-IBN (Konditionierung) über Begrenzung von 6,2 V | - " -
| August Do: September | RM9 | Betrieb für Engineering Run | - " -
| So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo |  | RM10 | Dritte HF-Leistungs-IBN (Konditionierung) für U4+ | - " -
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Sources: HSI-UR | September Mo: 40Ar1+/2+; September Mi: stdby |  | RF | RF Cond. for Uranium (HSI, Alvarez, TK) | - " -
HSI-RFQ | September Mo: RM4; September Fr: RM5; September Fr: RM6
[32 empty] | OP | Operator Training | - " -
[32 empty] | COM | Commission without beam | - " -
[32 empty] | U01 | RF Cond. for Uranium (HSI, Alvarez, TK) parallel Beam Setup with Ar | - " -
[32 empty] | U02 | Stable beam for TK (low prio: parallel beam to ex-hall) | - " -
| September So: October |  | U03 | switch to Uranium, when ready
| Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Sources: HSI-UL | October Di: 40Ar1+/2+; October Do: stdby | S01 | Beam Setup | Beam Setup
HSI + Alv. + TK | October Di: RF; October Mo: RM8
[32 empty] | S00/H00 | FAIR machine development | FAIR machine development
[32 empty] | S02 | Beam setup - prepare slow ext, fast ext, cooled beam | Machine Studies / Detector Tests
[32 empty] | S03 | Beam Setup - transfer to ESR | Machine Studies / Detector Tests
[32 empty] | S04 | Beam Setup - transfer to FRS | Machine Studies / Detector Tests
[32 empty] | S05 | stable beam parallel to ESR + FRS | Machine Studies / Detector Tests
| October Di: November | S06 | stable beam parallel to ESR + FRS, HEST beam setup (transfer ESR-Cryring) | Machine Studies / Detector Tests
| Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
HLI | November Mo: 40Ar1+; November Mi: standby - only in case of major HSI-RFQ-problems
Sources: HSI-UL | November Mo: 40Ar1+ |  | H01 | HHD for SIS Optimisation | Machine Studies / Detector Tests
Sources: HSI-UR | November Mo: 209Bi4+ |  | H02 | Transfer optimisation SIS-ESR | Machine Studies / Detector Tests
HLI | November Fr: Shutdown (work in cw-bunker) |  | H03 | Transfer optimisation FRS | Machine Studies / Detector Tests
HSI + Alv. + TK | November Sa: RM9; November Mo: U01; November Mi: U02; November Sa: S |  | H04 | Optics evaluation and optimisation HTC | Machine Studies / Detector Tests
SIS18 | November Mo: COM; November Mi: S01; November Do: S02; November Fr: S03; November Mo: S04; November Mi: S05; November Sa: M |  | H05 | Optics evaluation and optimisation HTA | Machine Studies / Detector Tests
HEST | November Mo: COM; November Mi: H01; November Fr: H02; November Mo: H03; November Mi: H04; November Fr: H05; November Di: H06; November Do: H07; November Sa: P |  | H06 | Transfer setup and optics evaluation HHT | Machine Studies / Detector Tests
ESR | November Di: delay; November Mo: E01; November Fr: E02; November Mi: E03; November Do: E04; November Sa: S |  | H07 | Optics evaluation and optimisation of transport ESR->CRYRING | Machine Studies / Detector Tests
FRS | November Mo: COM; November Mo: F00; November Fr: F01; November Mo: F02; November Do: F03; November Sa: M
Cryring | November Do: bake out extraction; November Fr: COM; November Mo: C00; November Sa: P
[32 empty] | E01 | Dry Test of Control System - storage ring mode | pause
[32 empty] | E02 | Beam setup (storage, cooling) | pause
[32 empty] | E03 | Beam setup (decceleration) | pause
[32 empty] | E04 | Beam setup (extraction) | pause
[32 empty] | E05 | stable beam for Cryring-Transfer | pause
December
| So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | [12 empty] | F00 | beam optimization for FRS | pause
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | [12 empty] | F01 | Primary beam SIS-TA, TA-S4, new SIS energy, detector signals, ID (including verification via tagging) | pause
Sources: HSI-UL | December Mo: 238U4+ (when ready) | [12 empty] | F02 | Beam to S8 (slow extraction) | pause
Sources: HSI-UR | December So: 209Bi4+ | [12 empty] | F03 | Beam to S6, fast extraction | pause
HLI | December So: Shutdown (work in cw-bunker) | [12 empty] | F04 | Training of people | pause
HSI + Alv. + TK | December Mo: RM10; December Mo: U03 | [12 empty] | F05 | Further options - Detector Tests | pause
SIS18 | December So: S06; December Di: S07; December Mo: S07; December Sa: S00
HEST | December So: H07; December Sa: H00
ESR | December So: E04; December Di: E05; December Mo: E05 | [12 empty] | C00 | Beam setup with local injector / Test extraction system | pause
FRS | December So: F04; December Mo: F05 | [12 empty] | C01 | optimize/match injecton into YR (0.8/ 1.4 Tm) | pause
Cryring | December Fr: C01; December Mo: C02; December Di: C03; December Mi: C04; December Do: C05; December Fr: C06; December Mo: C07; December Di: C08; December Mi: C09; December Do: C10 | [12 empty] | C02 | optimize stored beam at injection energy, incl. orbit (0.8/ 1.4 Tm) | pause
[32 empty] | C03 | setup cooling at injection energy | pause
[32 empty] | C04 | measure lifetime w/o cooling | pause
[32 empty] | C05 | setup deceleration from 1.4 Tm to 0.8 Tm | pause
[32 empty] | C06 | setup cooling at low rgidity | pause
[32 empty] | C07 | measure lifetime at low energy | pause
[32 empty] | C08 | Beam size/ position at 0.8 Tm | pause
[32 empty] | C09 | Tune Meas. to determine space charge limits | pause
[32 empty] | C10 | Test detector setups (move, scrape, measure) | pause
[32 empty] | SMP | Saturday Morning Physics 11:00-13:00

## Detailed incl. beam studies
[5 empty] | Day-Shifts | [5 empty] | (Night - shifts + Weekend)
|  |  | UL | UR | UNILAC | SIS18 | HEST | ESR | FRS | CRYRING | Beam Studies
November | 11 | Mo | 40Ar1+ | 40Ar | U01, UNILAC-AP-038.01 |  |  | E01 |  |  |  | U01 | RF Cond. for Uranium (HSI, Alvarez, TK) parallel Beam Setup with Ar
| 12 | Di |  |  | U01, UNILAC-AP-038.01 | [6 empty] | U02 | Stable beam for TK (low prio: parallel beam to ex-hall)
| 13 | Mi |  |  | U02, UNILAC-AP-022.01/2 | S01 | H01 |  |  |  |  | U03 | switch to Uranium, when ready
| 14 | Do |  |  | U02, UNILAC-AP-022.01/2 | S02 | H01
| 15 | Fr |  |  | U02, UNILAC-AP-022.01/2 | S03 | H02 | E02 |  |  |  | S01 | Beam Setup
| 16 | Sa | [8 empty] | SIS-AP-048.01, SIS-AP-049.01 (2 shifts) | S02 | Beam setup - prepare slow ext, fast ext, cooled beam
| 17 | So | [8 empty] | SIS-RF-043.01, SIS-AP-051.01, SIS-AP-056.01 | S03 | Beam Setup - transfer to ESR
| 18 | Mo |  |  | UNILAC-BI-032.01 | S04 | H03 |  | F00 | C00 |  | S04 | Beam Setup - transfer to FRS
| 19 | Di |  |  | UNILAC-BI-017.01 |  |  | ESR-BI-020.01 |  |  | ESR-BI-020.01 | S05 | stable beam parallel to ESR + FRS
| 20 | Mi |  |  | UNILAC-BI-017.01 | S05 | HEST-BI-014.01 | ESR-BI-046.01 |  |  | ESR-BI-046.01 | S06 | stable beam parallel to ESR + FRS, HEST
| 21 | Do |  |  |  | SIS18-BI-011.01 |  | ESR-EP-026.01 |  |  | ESR-EP-026.01
| 22 | Fr |  |  |  | SIS18-BI-011.01 |  | ESR-EP-028.01 | F01 |  | ESR-EP-028.01 | H01 | HHD for SIS Optimisation
| 23 | Sa | [8 empty] | HEST-BI-013.01 (3 shifts) | H02 | Transfer optimisation SIS-ESR
| 24 | So | [8 empty] | HEST-BI-013.01 (2 shifts) | H03 | Transfer optimisation FRS
| 25 | Mo |  | 209Bi4+ |  | S06 | H04 | E03 | F02 |  |  | H04 | Optics evaluation and optimisation HTC/HTD
| 26 | Di |  |  |  |  | HEST-EP-019.01 |  |  |  | HEST-EP-019.01 | H05 | Optics evaluation and optimisation HTA
| 27 | Mi |  |  |  |  | H05 |  |  |  |  | H06 | Transfer setup and optics evaluation HHT
| 28 | Do |  |  |  |  | HEST-EP-040.1 |  | F03 |  |  | H07 | Optics evaluation and optimisation of transport ESR->CRYRING
| 29 | Fr |  |  |  |  | HEST-BI-010.01 |  |  |  | HEST-BI-010.01
| 30 | Sa | [8 empty] | UNILAC-OP-021.01 , HEST-AP-031.01, HEST-AP-033.01 | E01 | Dry Test of Control System - storage ring mode
Dezember | 1 | So | [8 empty] | SIS18-AP-016.01 + SIS-AP-030.01 (3 shifts) | E02 | Beam setup (storage, cooling)
| 2 | Mo |  |  |  |  | H07 | E04 | F04 |  |  | E03 | Beam setup (decceleration)
| 3 | Di | [5 empty] | ESR-EP-027.01 |  |  | ESR-EP-027.01 | E04 | Beam setup (extraction)
| 4 | Mi | [6 empty] | FRS-BI-047.01 |  | FRS-BI-047.01 | E05 | stable beam for Cryring-Transfer
| 5 | Do | [5 empty] | E05 | FRS-BI-047.01 | C01 | FRS-BI-047.01
| 6 | Fr | [9 empty] | F00 | beam optimization for FRS
| 7 | Sa | [8 empty] | SIS18-BI-012.01 (3 shifts) | F01 | Primary beam SIS-TA, TA-S4, new SIS energy, detector signals, ID (including verification via tagging)
| 8 | So | [8 empty] | SIS-BI-045.01, SIS-RF-042.01 (2 shifts) | F02 | Beam to S8 (slow extraction)
| 9 | Mo | 238U4+ |  | U03 |  |  |  | F05 | C02 |  | F03 | Beam to S6, fast extraction
| 10 | Di | [7 empty] | C03 |  | F04 | Training of people
| 11 | Mi | [6 empty] | FRS-BI-024.01 | C04 | FRS-BI-024.01 | F05 | Further options - Detector Tests
| 12 | Do | [6 empty] | FRS-EP-025.01 | C05 | FRS-EP-025.01
| 13 | Fr | [7 empty] | C06
| 14 | Sa | [8 empty] | SIS-AP-060.01, SIS-AP-055.01, | C00 | Beam setup with local injector / Test extraction system
| 15 | So | [8 empty] | SIS-AP-058.01, SIS-AP-050.01 (2 shifts) | C01 | optimize/match injecton into YR (0.8/ 1.4 Tm)
| 16 | Mo | [7 empty] | C07 | Operator exam | C02 | optimize stored beam at injection energy, incl. orbit (0.8/ 1.4 Tm)
| 17 | Di | [7 empty] | C08 | Operator exam | C03 | setup cooling at injection energy
| 18 | Mi | [7 empty] | C09 |  | C04 | measure lifetime w/o cooling
| 19 | Do | [7 empty] | C10 |  | C05 | setup deceleration from 1.4 Tm to 0.8 Tm
[12 empty] | C06 | setup cooling at low rgidity
[12 empty] | C07 | measure lifetime at low energy
[12 empty] | C08 | Beam size/ position at 0.8 Tm
[12 empty] | C09 | Tune Meas. to determine space charge limits
[12 empty] | C10 | Test detector setups (move, scrape, measure)