## Slide 1: Super-FRS components
Haik Simon
FAIR-BINP Workshop Novosibirsk, November 25-29, 2019
Haik Simon / FAIR-BINP Workshop, Novosibirsk, November 25-29, 2019

## Slide 2: Delivery Matrix
First of Series

## Slide 3: Super-FRS Magnets Radiation Resistant Dipoles
Scope:
2 nc dipoles using MIC cable
(one prototype dipole built at BINP, already tested)
Dedicated support structure
Remote connectors and alignment
≈95 ton
interfaces: sextupole, beam catcher, pillow seal
Target Area
  Status / Schedule
Detailed specs (including support) released
MIC ordered by FAIR
Contract signed on 15/03/2019 Regular reports not received (dash board?)
Production plan review: 08/2019  expected this workshop
Conceptual Design Review*: 08/2019  expected this workshop
Final Design Review**: 12/2019  to be agreed in this workshop
** payment to be done (2019?)
** payment shifted to 2020

## Slide 4: Super-FRS Magnets Radiation Resistant Multipoles
Scope:
3 nc quadrupoles and 2 nc sextupoles
Dedicated support structure
Remote connectors and alignment
≈30 ton
≈30 ton
interfaces: dipole, beam catcher, pillow seal, support structure
  Status / Schedule
Detailed specs (including support) released for each magnet, but new insight required
R&D contract signed on 16/09/2019
R&D first results relevant for contract: 11/2019
Critical decision: can we achieve this within this workshop?
Contract signature: Dec 2019
Conceptual Design Review: Mar 2020
Final Design Review: Sep 2020
Manufacturing: till July 2022
SAT: till January 2023
Installation: from January 2023

## Slide 5: Super-FRS Vacuum NC dipoles chambers
Scope:
3 nc dipoles chambers withstanding high radiation
Installation on site must be technically feasible
  Status / Schedule
EoI
R&D contract signed on 11/09/2019
Preliminary design review (PDR) with preliminary 3D-Model: Mid-term meeting in May 2020
Fulfilment of research on Super-FRS primary beam absorber for dipole chamber: Nov 2020
Specifications: Nov-Dec 2020
Contract signature: Jan-Feb 2021
Final Design Review: Mar-Apr 2021
Manufacturing: in line with nc dipoles
ongoing …

## Slide 6: Super-FRS Vacuum NC multipoles chambers
Scope:
3 nc quadrupoles chambers
2 nc sextupoles chambers
Installation on site must be technically feasible
  Status / Schedule
EoI
Detailed specs for chamber released 04/2019 (there could be need for minor adjustment due to ongoing R&D on nc multipoles)
scheduling directly coupled to nc multipole‘s
Contract 12/2019 (?, together with nc multipoles)

## Slide 7: Super-FRS Vacuum SC standard-dipoles chambers
Scope:
21 vacuum chambers for sc standard dipoles including pumping ports
installation services
  Status / Schedule
Detailed specs released
Contract signed on 11/09/2019
CDR FoS: Nov 2019 no document received
FDR FoS: Feb 2020
CDR series: Mar 2020
FAT and delivery FoS: Apr 2020
FDR series: May 2020
Manufacturing: May 2020 – Feb 2022
End of FAT series: Feb 2022
End of SAT: Apr 2022
End of installation services: Apr 2022
Final acceptance: Apr 2022
scheduling in line with nc magnets
Reporting …

## Slide 8: Super-FRS Vacuum SC branched-dipoles chambers
Scope:
3 sc branched-dipoles chambers
  Status / Schedule
EoI received long time ago
chamber's specs released (included in magnets’ specs)
Design of magnet CDR CEA: Q1/2019
Magnet production scheme allows for integration of BINP chamber in the assembly scheme
Manufacturing expected together with branched dipoles (currently 2021)
Technical discussion in the workshop

## Slide 9: Super-FRS Vacuum Diagnostic (focal-plan) chambers
FLF2
Scope:
21 focal-plan chambers
corresponding supports
  Status / Schedule
Detailed specifications released
Contract signed on 15/03/2019
CDR FoS: 06/2019 received 09/2019
FDR FoS*: 09/2019 not received
CDR series*: 12/2019 request to shift to 2020
agree on schedule within this workshop
FAT and delivery FoS: 02/2020
SAT FOS: 05/2020 (problem to assign hall space if dates are not reliable)
FDR series: Mar 2020
Manufacturing: Mar 2020 – Aug 2021 (details on shipment to be decided)
End of FAT: Aug 2021
End of SAT: Nov 2021
Final acceptance: Nov 2021
* payment shifted to 2020
?

## Slide 10: Super-FRS Vacuum Beam pipes, bellows, pumping chambers
PSP-Code | Description | Pieces Units | Inst. | Country | Status | Res.-No.
2.4.7.1.11 | Beam pipe (various length) | 13 | BINP | Russia | Council | VI.8.3
2.4.7.1.14 | Pumping chamber | 31 |  |  | NEW | 
2.4.7.1.15.1 | Beam pipe (various length) part 2 | 28 |  |  | NEW | 
2.4.7.1.15.2 | Beam pipe/pumping chamber support | 47 |  |  | NEW | 
2.4.7.4.2 | Bellow (L=150, D=400) | 66 | BINP | Russia | Council | VI.8.3
2.4.7.4.3 | Bellow (L=150, D=400) part 2 | 18 |  |  | NEW | 
Scope:
203 vacuum elements: beam pipes, supports, bellows, pumping chambers
  Status / Schedule
79 elements already assigned to BINP
Manufacturing flexible but installation during 2023
pieces are required in time for pre-assembly
contracts expected within 2020 in batches to be discussed
CB8
CB8

## Slide 11: Super-FRS Beam Instrumentation BPM
Scope:
Beam Position Monitor (Pick-up)
  Status / Schedule
topic at BINP workshop (11/2018)
Design of TCR1 BPM by BINP existing
we aiming for CC with BINP adapting BINP`s design
  Detailed specs sent to BINP contact (Yury Rogovsky) on 04/06/2019
  meeting with Y. Rogovsky on 22.10.19
  additional design work requested by BINP a week ago
  design adaption needed due to large y dimension
Consider as amendment to focal plane chamber contract
Design activities could be supported
TCR1 BPM
by BINP

## Slide 12: Super-FRS Local cryogenics
~ 120 t of
stainless steel
Scope:
1 large Branch Box
Feedboxes (≈60)
End Boxes (7)
≈60 Jumper connections (≈250 m)
Transferlines (≈300 m)
1 large Branch Box
≈1.5 km Warm-Gas Piping
  Status
  DMU concept ready
  Common/detailed specs released (= scope definition)
  technical scope and realization scheme quite advanced

## Slide 13: Super-FRS Local cryogenics
Deliverables: Dec 2021 – Oct 2022
Installation others: Oct 2022 – Dec 2022
Installation warm piping: Mar 2022
Partition of technical scope to be defined
09/2019
09/2019

## Slide 14: support transparencies

## Slide 15: sc standard dipoles (July 2019)
ELYTT Nombre de tarea | Finish FAT
FoS Dipole Type 3 (01) ready to go | 19/03/2020
FoS Dipole Type 2 (02) ready to go | 10/09/2020
Dipole Type 3 AO (03) ready to go | 23/10/2020
Dipole Type 3 AO (04) ready to go | 01/12/2020
Dipole Type 3 AO (05) ready to go | 22/01/2021
Dipole Type 3 AO (06) ready to go | 01/03/2021
Dipole Type 3 AO (07) ready to go | 14/04/2021
Dipole Type 2 (08) ready to go | 20/05/2021
Dipole Type 2 (09) ready to go | 25/06/2021
Dipole Type 3 B0 (10) ready to go | 24/08/2021
Dipole Type 3 B0 (11) ready to go | 29/09/2021
Dipole Type 3 B0 (12) ready to go | 04/11/2021
Dipole Type 3 B0 (13) ready to go | 13/12/2021
Dipole Type 3 B0 (14) ready to go | 28/01/2022
Dipole Type 3 B0 (15) ready to go | 07/03/2022
Dipole Type 3 B0 (16) ready to go | 20/04/2022
Dipole Type 3 B2 (17) ready to go | 26/05/2022
Dipole Type 3 C0 (18) ready to go | 01/07/2022
Dipole Type 3 C1 (19) ready to go | 30/08/2022
Dipole Type 3 D2 (20) ready to go | 05/10/2022
Dipole Type 2 D2 (21) ready to go | 11/11/2022

## Slide 16: Extract from CB8
last sextupole on the support of beam catcher

## Slide 17: Extract from CB8

## Slide 18: Super-FRS Local cryogenics

## Slide 19: Super-FRS layout
LM_01
LM_02
DC_01
LM_03
TA
NC_QQ
NC_QS
NC_D1
NC_D2
NC_D3
BC1
BC2
BC3-NCS
SM_01
SM_03
SM_02
DC_02
SM_04
SM_05
SM_06
SM_07
FTF1
FPF0
FPF1
FPF2
FPF3
FPF4
FMF1
FMF2
FMF3
FRF1
DC_18
FRF2
FRF3
DC_19
DC_20
FHF1
FLF1
DC_10
DC_11
DC_12
DC_13
DC_14 (maybe)
FLF2
FLF3
FLF4
DC_15
FLF5
DC_16
FLF6
DC_17
DC_09
DC_07
DC_03
DC_04
DC_05
DC_08
DC_06
SCD_01
SCD_02
SCD_03
LM_04
LM_05
SCD_04
SCD_05
SCD_06
LM_06
SCD_07
SCD_08
SCD_09
LM_07
LM_08
LM_09
SCD_10
SCD_11 (branch)
SCD_12
LM_10
LM_11
FHF2
FHF3
LM_12
LM_13
GLAD
SCD_13
LM_14
LM_15
LM_16
LM_17
LM_18
LM_19
LM_20
LM_21
LM_22
LM_23
SCD_14 (branch)
SCD_15
SCD_16
SCD_17
SCD_18
SCD_19
SCD_21
SCD_20
SCD_22
SCD_23 (branch)
SCD_24
EBM_01
EBM_02
EBM_03
EBM_04
EBM_05
EBD_01
EBD_02
EBD_03
Assembly Units
along the beamline
NC_QQ nc quadrupole 1a + quadrupole 1b
NC_QS nc quadrupole 2 + sextupole
NC_D nc dipole
BC beam catcher
BC3-NCS beam catcher 3 + nc sextupole
TA target chamber
DC diagnostic chamber
SM sc short multiplet
LM sc long multiplet
SCD sc dipole
VAC vacuum part
EBD EB dipole
EBM EB multiplet
BDN Beam dump NUSTAR
VAC_02
VAC_07
VAC_08
VAC_10
VAC_11
VAC_03
VAC_04
VAC_ NUSTAR
VAC_01
VAC_09
BDN
VAC_05
VAC_06