## Slide 1: Pre assembly SuperFRS for Elytt magnets
Haik Simon
FAIR-BINP Workshop Novosibirsk, November 25-29, 2019
Haik Simon / FAIR-BINP Workshop, Novosibirsk, November 25-29, 2019

## Slide 2: Super-FRS layout
LM_01
LM_02
DC_01
LM_03
TA
NC_QQ
NC_QS
NC_D1
NC_D2
NC_D3
BC1
BC2
BC3-NCS
SM_01
SM_03
SM_02
DC_02
SM_04
SM_05
SM_06
SM_07
FTF1
FPF0
FPF1
FPF2
FPF3
FPF4
FMF1
FMF2
FMF3
FRF1
DC_18
FRF2
FRF3
DC_19
DC_20
FHF1
FLF1
DC_10
DC_11
DC_12
DC_13
DC_14 (maybe)
FLF2
FLF3
FLF4
DC_15
FLF5
DC_16
FLF6
DC_17
DC_09
DC_07
DC_03
DC_04
DC_05
DC_08
DC_06
SCD_01
SCD_02
SCD_03
LM_04
LM_05
SCD_04
SCD_05
SCD_06
LM_06
SCD_07
SCD_08
SCD_09
LM_07
LM_08
LM_09
SCD_10
SCD_11 (branch)
SCD_12
LM_10
LM_11
FHF2
FHF3
LM_12
LM_13
GLAD
SCD_13
LM_14
LM_15
LM_16
LM_17
LM_18
LM_19
LM_20
LM_21
LM_22
LM_23
SCD_14 (branch)
SCD_15
SCD_16
SCD_17
SCD_18
SCD_19
SCD_21
SCD_20
SCD_22
SCD_23 (branch)
SCD_24
EBM_01
EBM_02
EBM_03
EBM_04
EBM_05
EBD_01
EBD_02
EBD_03
Assembly Units
along the beamline
NC_QQ nc quadrupole 1a + quadrupole 1b
NC_QS nc quadrupole 2 + sextupole
NC_D nc dipole
BC beam catcher
BC3-NCS beam catcher 3 + nc sextupole
TA target chamber
DC diagnostic chamber
SM sc short multiplet
LM sc long multiplet
SCD sc dipole
VAC vacuum part
EBD EB dipole
EBM EB multiplet
BDN Beam dump NUSTAR
VAC_02
VAC_07
VAC_08
VAC_10
VAC_11
VAC_03
VAC_04
VAC_ NUSTAR
VAC_01
VAC_09
BDN
VAC_05
VAC_06

## Slide 3: Delivery Matrix
First of Series

## Slide 4: Super-FRS Vacuum SC standard-dipoles chambers
Scope:
21 vacuum chambers for sc standard dipoles including pumping ports
installation services
  Status / Schedule
Detailed specs released
Contract signed on 11/09/2019
CDR FoS: Nov 2019
FDR FoS: Feb 2020
CDR series: Mar 2020
FAT and delivery FoS: Apr 2020
FDR series: May 2020
Manufacturing: May 2020 – Feb 2022
End of FAT series: Feb 2022
End of SAT: Apr 2022
End of installation services: Apr 2022
Final acceptance: Apr 2022
scheduling in line with nc magnets
Reporting …

## Slide 5: Super-FRS Vacuum SC branched-dipoles chambers
Scope:
3 sc branched-dipoles chambers
  Status / Schedule
EoI received long time ago
chamber's specs released (included in magnets’ specs)
Design of magnet CDR CEA: Q1/2019
Magnet production scheme allows for integration of BINP chamber in the assembly scheme
Manufacturing expected together with branched dipoles (currently 2021)
Technical discussion in the workshop

## Slide 6: Hall space (~60 x 20 = 1200 m²)
Deliver directly to site:
# Magnet + chamber without end flanges
+Single crane operation
+Transport to installation place via air cushion
+No additional storage space needed.
crane missing  lifting tool 25t required
Floor at -3m  fork lift, tools require transport
Truck onloading

## Slide 7: Super-FRS D3y – branched SC dipoles
Summary of 15/06/2018 presentation
A. Madur on behalf of
Patrick GRAFFIN, Michaël MASSINGER, Hugo REYMOND
Notes: I’ll present you the mecanical part of the special magnet 9,75°

## Slide 8: Super-FRS D3y

## Slide 9
It‘s movie time

## Slide 10: Overview D3Y 9.75° or branched dipole

## Slide 11: Geometry Cold mass
2407
1213
2257
950
620
20°
The 2 horizontal cold to warm supports :
allow lateral adjustment of the cold mass
420
655
20°
2400
The 4 vertical cold to warm supports :
allow the vertical adjustment of the cold mass
The 4 tilted cold to warm supports :
reduce the movement of the cold mass during energizing phase

## Slide 12: Geometry Cold mass
70°
Cold to warm supports (x10)
Adjustable pillars M24 (± 7 mm)
Notes: CTWS : +- 5mm
Pillar :

## Slide 13: Cryostat

## Slide 14: Beam Chamber
Old
New

## Slide 15: Beam Chamber
Fixing Part
Thickness :
Plate : 10 mm
Base Plate : 15 mm
Flange
Thickness : 28 mm
Flange
Thickness : 28 mm
Chamber
Thickness : 12 mm
Flange
Thickness : 34 mm
Fixing Part
Thickness :
Plate : 10 mm
Base Plate : 15 mm
Fixing Part
Thickness :
Plate : 10 mm
Base Plate : 15 mm
Fixing Part
Thickness :
Plate : 10 mm
Base Plate : 15 mm
Machining Part

## Slide 16: Beam Chamber
UX=UY=UZ=0
UX=UY=UZ=0
UX=UY=UZ=0
UX=UY=UZ=0
UX=UY=UZ=0
UX=UY=UZ=0
UX=UY=0
Vacuum in the beam chamber (External Pressure : 0,1 Mpa)
X
Y
Z

## Slide 17: Beam Chamber Vacuum
Displacement
Uz =10.5 mm
Old

## Slide 18: Beam Chamber Vacuum
Displacement
Uz = 1.09 mm
New

## Slide 19: Beam Chamber Vacuum
Von-Mises
Old

## Slide 20: Beam Chamber Vacuum
A
A
(122 MPa)
Max 108 MPa
Von-Mises
A
A
New

## Slide 21: Beam Chamber Vacuum
Max 122 MPa
Tresca
Max 138 MPa

## Slide 22: Beam Chamber Vacuum
Max 116 MPa
Max 93 MPa
Max 138 MPa

## Slide 23: Beam Chamber Vacuum
Max 116 MPa
Max 93 MPa
Max 138 MPa

## Slide 24: Beam Chamber Vacuum
Max 116 MPa
Max 93 MPa
Max 138 MPa

## Slide 25: Beam Chamber Vacuum
Max 116 MPa
Max 93 MPa
Max 138 MPa

## Slide 26: Beam Chamber Vacuum
Max 116 MPa
Max 93 MPa
Max 138 MPa

## Slide 27: Beam Chamber Vacuum
Max 116 MPa
Max 93 MPa
Max 138 MPa