## BINP all
Delivery Matrix BINP all components
| Clarify contract details (column F) | contract open | Latest delivery date assumption by WPL, scheduling coordination between FAIR/GSI and BINP is needed. | [6 empty] | To be discussed |  |  | Latest delivery date from contract, detailed production scheduling is to be provided by BINP.
|  | Assembly | Well timed delivery of magnet and corresponding vacuum chamber. | [6 empty] | To be discussed |  |  | Components delayed according to latest BINP production plan.
| To be discussed during BINP Workshop | Assembly | Coordination between delivery of magnet and corresponding vacuum chamber is needed. Vacuum chamber arrives later than magnet.
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Quantity | Work Package | Assembly | Start delivery | Finish delivery | Contract status | delivered | 1: 2020; 1: 2021; 1: 2022; 1: 2023
1771 | HEBT |  |  |  |  | 27 | 1: 122; 2: 23; 3: 24; 5: 25; 6: 2; 7: 12; 8: 73; 9: 8; 10: 111; 11: 18; 12: 10; 1: 4; 2: 8; 3: 95; 4: 4; 6: 23; 10: 1175; 12: 7
310 | HEBT Magnets |  |  |  |  | 27 | 1: 122; 2: 23; 3: 8; 5: 25; 6: 2; 7: 8; 8: 8; 9: 8; 10: 15; 11: 12; 12: 10; 2: 8; 4: 4; 6: 23; 12: 7
6 | Dipole 10 (HEBT 100 Divider) - dip10 | HEBT dip10 | 2019-08-01 | 01/20 | signed |  | 1: 6
4 | Dipole 15 (HEBT18) - dip15_0 | HEBT dip15 | 2019-09-01 | 2019-09-01 | signed | 4
1 | Dipole 15 (HEBT18) - dip15_1 | HEBT dip15 | 2019-07-01 | 2020-01-01 | signed | bar: 1
1 | Dipole 16 (HEBT18) - dip16 | HEBT dip16 | 2019-07-01 | 2020-01-01 | signed | bar: 1
1 | Dipole 17 (HEBT18) - dip17_0 | HEBT dip17 | 2019-09-01 | 2020-01-01 | signed | bar: 1
4 | Dipole 19 (HEBT100) - dip19_0 | HEBT dip19 | 2019-09-01 | 2020-02-01 | signed |  | 1: 3; 2: 1
2 | Dipole 13 (SIS100) - dip13_0 | HEBT dip13 | 2019-08-01 | 2020-01-01 | signed |  | 1: 2
3 | Dipole 13 (SIS100) - dip13_3 | HEBT dip13 | 2019-11-01 | 2020-01-01 | signed |  | 1: 3
2 | Dipole 4 - dip4 FBL | HEBT dip4 FBL | 2021-06-01 | 2021-06-01 | signed |  | 4: 2
2 | CR-type dip3_3 | CR-type dip3_3 | 2021-12-01 | 2021-12-01 | open |  | 10: 2
81 | Quadrupole 2 (SIS18 HEBT-Type long) | HEBT quad2 | 2018-11-01 | 2020-12-01 | signed | 17 | 1: 35; 2: 7; 8: 8; 10: 7; 12: 7
4 | Quadrupole 10 (CBM Target-Focus Type long) | HEBT quad10 | 2019-07-01 | 2020-01-01 | signed |  | 1: 4
69 | Quadrupole 11 (HEBT100) | HEBT quad11 | 2019-07-01 | 2021-04-01 | signed |  | 1: 25; 5: 8; 7: 8; 10: 8; 11: 8; 2: 8; 4: 4
12 | Quadrupole 12 (HEBT100) | HEBT quad12 | 2019-11-01 | 2020-05-01 | signed |  | 1: 5; 3: 4; 5: 3
1 | Quadrupole 1 FBL | HEBT quad1 FBL | 2021-06-01 | 2021-06-01 | signed | bar: 4 to 6
9 | Quadrupole 2 FBL | HEBT quad2 FBL | 2021-06-01 | 2021-06-01 | signed |  | 4: 9
4 | Quadrupole 2 (SIS18 HEBT-Type long) HED | HEBT quad2 HED | 2021-06-01 | 2021-06-01 | signed |  | 4: 4
1 | Quadrupole 11 (HEBT100) HED | HED quad11 HED | 2021-06-01 | 2021-06-01 | signed | bar: 4 to 6
5 | CR-type quad3_3 | CR-type quad3_3 | 2021-12-01 | 2021-12-01 | open |  | 10: 5
5 | Steering Magnets HEBT18 (large aperture) | HEBT S18 (large) | 2020-05-01 | 2020-09-01 | signed |  | 5: 1; 9: 4
44 | Steering Magnets HEBT18 | HEBT S18 | 2019-06-01 | 2020-12-01 | signed | 2 | 1: 18; 2: 4; 3: 4; 5: 3; 6: 2; 9: 4; 11: 4; 12: 3
43 | Steering Magnets HEBT100 | HEBT S100 | 2019-06-01 | 2020-05-01 | signed | 4 | 1: 18; 2: 11; 5: 10
2 | Steering Magnet HEBT100 HED | HEBT S100 HED | 2021-06-01 | 2021-06-01 | signed |  | 4: 2
4 | Steering Magnet HEBT18 FBL | HEBT S18 FBL | 2021-06-01 | 2021-06-01 | signed |  | 4: 4
1461 | HEBT Vacuum | [5 empty] | 3: 16; 7: 4; 8: 65; 10: 96; 11: 6; 1: 4; 3: 95; 10: 1175
6 | Dipole chamber dip 10 Divider | HEBT dip10 | 2020-11-01 | 2020-11-01 | signed |  | 9: 6
5 | Dipole chamber dip 13 | HEBT dip13 | 2020-03-01 | 2020-03-01 | signed |  | 1: 5
5 | Dipole chanber dip 15 | HEBT dip15 | 2020-03-01 | 2020-03-01 | signed |  | 1: 5
1 | Dipole chamber dip 16 | HEBT dip16 | 2020-03-01 | 2020-03-01 | signed | bar: 3
1 | Dipole chamber dip 17 | HEBT dip17 | 2020-03-01 | 2020-03-01 | signed | bar: 3
4 | Dipole chamber dip 19 | HEBT dip19 | 2020-07-01 | 2020-07-01 | signed |  | 5: 4
1 | Dipole chamber dip 4 (bending) FBL | HEBT dip4 FBL | 2021-03-01 | 2021-03-01 | signed | bar: 3
1 | Dipole chamber dip 4 (branching) FBL | HEBT dip4 FBL | 2021-03-01 | 2021-03-01 | signed | bar: 3
2 | CR-Type Dipole Chamber dip3_3 | CR-type dip3_3 | 2021-03-01 | 2021-03-01 | open |  | 2: 2
4 | Quadrupole chamber quad10 | HEBT quad10 | 2020-03-01 | 2020-03-01 | signed |  | 1: 4
69 | Quadrupole chamber quad 11 | HEBT quad11 | 2021-03-01 | 2021-03-01 | signed |  | 1: 69
17 | Quadrupole chamber quad 12 | HEBT quad12 | 2021-03-01 | 2021-03-01 | signed |  | 1: 17
81 | Quadrupole chamber quad 2 | HEBT quad2 | 2020-10-01 | 2020-10-01 | signed |  | 8: 81
9 | Quadrupole chamber quad 2 FBL | HEBT quad2 FBL | 2020-10-01 | 2020-10-01 | signed |  | 8: 9
1 | Quadrupole Chamber quad1 FBL | HEBT quad1 FBL | 2020-10-01 | 2020-10-01 | signed | bar: 10
4 | Quadrupole Chamber quad2 HED | HEBT quad2 HED | 2020-10-01 | 2020-10-01 | not assigned |  | 8: 4
1 | Quadrupole Chamber quad11 HED | HED quad11 HED | 2020-10-01 | 2020-10-01 | not assigned | bar: 10
5 | CR-Type Quadrupole Chamber quad3_3 | CR-type quad3_3 | 2021-03-01 | 2021-03-01 | open |  | 1: 5
29 | Steerer chamber s100 | HEBT S100 | 2020-08-01 | 2020-08-01 | signed |  | 6: 29
2 | Steerer Chambers s100 HED | HEBT S100 HED | 2020-08-01 | 2020-08-01 | not assigned |  | 7: 2
31 | Steerer chamber s18h/v | HEBT S18 | 2020-08-01 | 2020-08-01 | signed |  | 6: 31
3 | Steerer chamber s18h/v FBL | HEBT S18 FBL | 2020-08-01 | 2020-08-01 | signed |  | 6: 3
4 | Steerer chamber s13 large aperture | HEBT S18 (large) | 2021-01-01 | 2021-01-01 | signed |  | 11: 4
1175 | Batch 4 (Bellows, Pumping Chambers, Straight Tubes) |  | 2021-10-01 | 2021-10-01 | open |  | 8: 1175
701 | CR | [10 empty] | 1 | 5 |  | 3 | 6 | 8 | 233 | 21 | 10 | 30 | 14 | 36 | 15 | 17 | 18 | 23 | 16 | 58 | 16 | 16 | 11 | 13 | 10 | 15 | 21 | 18 | 16 | 6 | 5 | 7 | 3 | 4 | 4 | 3 | 2 | 7 | 4 | 1 | 4 | 1
140 | CR Magnets | [11 empty] | 1 |  |  | 1 |  | 1 | 3 | 2 | 5 | 4 | 3 | 5 | 3 | 4 | 8 | 6 | 5 | 6 | 6 | 4 | 5 | 5 | 6 | 5 | 5 | 5 | 4 | 3 | 5 | 3 | 2 | 3 | 3 | 2 | 7 | 4 | 1 | 4 | 1
26 | CR/TCR1 Dipole Magnet | CR/TCR1 dip | 2020-07-01 | 2023-08-01 | signed |  | 7: 1; 1: 1; 2: 1; 3: 1; 5: 1; 6: 1; 8: 1; 9: 1; 10: 1; 12: 1; 1: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 10: 1; 11: 1; 12: 1; 2: 1; 3: 1; 5: 1; 6: 1; 8: 2
29 | CR Wide Quadrupoles | CR quad wide / sext | 2020-10-01 | 2023-08-01 | signed |  | 10: 1; 3: 2; 4: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1
5 | TCR1 Wide Quadrupoles | TCR1 quad wide | 2023-05-01 | 2023-06-01 | signed |  | 5: 3; 6: 2
11 | CR Narrow Quadrupoles | CR quad narrow | 2020-12-01 | 2023-09-01 | signed | bar: 12; 2; 5; 9; 1; 5; 9; 1; 5; 8 to 9
1 | TCR1 Narrow Septum Quadrupole | CR quad narrow | 2021-10-01 | 2021-10-01 | signed | bar: 10
26 | CR/TCR1 Sextupole Magnets | CR quad wide / sext | 2021-04-01 | 2023-05-01 | signed | bar: 4 to 5
12 | CR Octupole Correctors | CR quad wide / sext | 2021-09-01 | 2022-07-01 | signed |  | 9: 2; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1
3 | CR Injection Septum |  | 2021-11-01 | 2022-11-01 | signed |  | 11: 1; 11: 2
1 | CR Extr. Septum magnet |  | 2022-08-01 | 2022-08-01 | signed | bar: 8
4 | CR Combined Steering Magnets | CR/TCR1 steerer | 2021-04-01 | 2021-12-01 | signed | bar: 4; 6; 9; 12
21 | CR/TCR1 Vertical Steering Magnets | CR/TCR1 steerer | 2021-01-01 | 2022-09-01 | signed |  | 1: 2; 3: 2; 4: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1
1 | TCR1 Combined Steering Magnets | CR/TCR1 steerer | 2022-03-01 | 2022-03-01 | signed | bar: 3
415 | CR Vacuum | [5 empty] | 7: 3; 9: 2; 10: 4; 11: 6; 12: 229; 1: 14; 2: 5; 3: 21; 4: 8; 5: 30; 6: 7; 7: 8; 8: 8; 9: 7; 10: 5; 11: 48; 12: 6; 1: 4
24 | CR Dipole Chamber | CR/TCR1 dip | 2020-07-01 | 2022-01-01 | signed |  | 7: 1; 11: 2; 12: 2; 1: 2; 5: 2; 6: 3; 7: 3; 11: 2; 12: 4; 1: 3
2 | TCR1 Dipole Chamber | CR/TCR1 dip | 2021-10-01 | 2021-12-01 | signed | bar: 10; 12
29 | CR Wide Quad+Sext Chamber | CR quad wide / sext | 2020-07-01 | 2021-11-01 | signed |  | 7: 2; 9: 2; 10: 4; 11: 3; 3: 2; 4: 4; 5: 3; 6: 1; 7: 1; 8: 2; 9: 1; 10: 3; 11: 1
6 | TCR1 Wide Quadrupole Chamber | TCR1 quad wide | 2021-08-01 | 2021-09-01 | signed |  | 8: 4; 9: 2
43 | Straight Tubes | CR quad narrow | 2020-11-01 | 2021-09-01 | signed |  | 11: 1; 12: 2; 1: 8; 2: 5; 3: 4; 4: 4; 5: 2; 6: 3; 7: 3; 8: 2; 9: 4; 10: 1; 11: 2; 12: 1; 1: 1
311 | Pumps/Valves/Roughing Stations/Adaptors/Support Frames |  | 2020-12-01 | 2021-11-01 | signed |  | 12: 225; 1: 4; 3: 15; 5: 23; 7: 1; 11: 43
103 | CR Power Converter | [5 empty] | 11: 1; 12: 2; 1: 1; 2: 2; 3: 2; 4: 1; 5: 2; 6: 3; 7: 5; 8: 4; 9: 6; 10: 4; 11: 4; 12: 4; 1: 5; 2: 6; 3: 6; 4: 5; 5: 7; 6: 11; 7: 11; 8: 8; 9: 1; 10: 1; 11: 1
1 | CR Dipole Power Conveter |  | 2022-07-01 | 2022-07-01 | signed | bar: 7
2 | TCR1 Dipole Power Conveter |  | 2022-10-01 | 2022-11-01 | signed | bar: 10 to 11
15 | CR Quadrupole Power Conveter |  | 2021-06-01 | 2022-08-01 | signed |  | 6: 1; 5: 2; 6: 5; 7: 4; 8: 3
6 | TCR1 Quadrupole Power Conveter |  | 2021-09-01 | 2022-08-01 | signed | bar: 9; 4 to 8
6 | CR Sextupole Power Conveter |  | 2021-05-01 | 2022-09-01 | signed | bar: 5; 5 to 9
2 | TCR1 Sextupole Power Conveter |  | 2022-02-01 | 2022-03-01 | signed | bar: 2 to 3
48 | CR Steering Magnet Power Conveter |  | 2020-12-01 | 2022-08-01 | signed |  | 12: 1; 6: 1; 7: 4; 8: 3; 9: 4; 10: 3; 11: 3; 12: 3; 1: 3; 2: 3; 3: 4; 4: 3; 5: 3; 6: 4; 7: 3; 8: 3
7 | TCR1 Steering Magnet Power Conveter |  | 2021-02-01 | 2022-03-01 | signed |  | 2: 1; 12: 1; 1: 2; 2: 2; 3: 1
12 | CR Octupole Power Conveter |  | 2020-11-01 | 2021-10-01 | signed | bar: 11 to 10
4 | CR Injection/Extraction Power Conveter |  | 2021-03-01 | 2022-07-01 | signed | bar: 3; 11; 4; 7
41 | CR Beam Instrumentation | [5 empty] | 6: 1; 7: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 3; 2: 1; 3: 2; 4: 1; 5: 1; 7: 1; 8: 1; 9: 2; 10: 1; 11: 1; 1: 1; 2: 1; 3: 2; 5: 2; 6: 4; 7: 2; 8: 3; 9: 1; 10: 1; 11: 1; 1: 2; 2: 1
1 | DC Transformer |  | 2021-10-01 | 2021-10-01 | signed | bar: 10
19 | CR Beam Postition Monitors | CR/TCR1 steerer | 2020-06-01 | 2023-02-01 | signed | bar: 6 to 7; 9; 11; 1; 3; 5; 7; 9; 11; 1; 3; 5; 7 to 8; 10 to 11; 1 to 2
3 | TCR1 Beam Position Monitors | CR/TCR1 steerer | 2022-06-01 | 2022-08-01 | signed | bar: 6 to 8
1 | CR Fast Current Transformer |  | 2020-10-01 | 2022-05-01 | signed | bar: 10
1 | TCR1 Fast Current Transformer |  | 2020-10-01 | 2022-05-01 | open | bar: 5
1 | CR Residual Gas Profile Monitor |  | 2022-06-01 | 2022-06-01 | signed | bar: 6
5 | CR Scintillation Screen |  | 2020-12-01 | 2022-08-01 | signed | bar: 12; 2; 8; 2; 8
3 | TCR1 Scintillation Screen |  | 2021-04-01 | 2023-01-01 | open | bar: 4; 6; 1
2 | CR Beam Stopper |  | 2021-01-01 | 2022-06-01 | signed | bar: 1; 6
5 | CR Beam Scraper |  | 2021-01-01 | 2022-09-01 | signed | bar: 1; 3; 9; 3; 9
2 | CR Injection/Extraction | bar: 8; 6
2 | Injection/Extraction Kickers |  | 2021-08-01 | 2022-06-01 | signed | bar: 8; 6
169 | pbar | [5 empty] | 3: 2; 7: 2; 8: 4; 9: 2; 10: 13; 11: 8; 12: 2; 1: 1; 2: 2; 3: 2; 4: 1; 5: 116; 6: 6; 12: 5
23 | pbar Magnets | [5 empty] | 3: 2; 7: 1; 8: 2; 9: 1; 10: 5; 11: 2; 12: 1; 1: 1; 2: 2; 3: 1; 4: 1; 5: 4
1 | Bending Magnet |  | 2022-04-01 | 2022-04-01 | open | bar: 4
2 | CR-type narrow quad. Radiation hard |  | 2021-10-01 | 2022-03-01 | open | bar: 10; 3
1 | Wide quad. Radiation hard |  | 2021-10-01 | 2021-10-01 | open | bar: 10
4 | Sextupole wide | pbar Sextupole | 2022-05-01 | 2022-05-01 | open |  | 5: 4
3 | Steerer horizontal | pbar Steerer h | 2021-03-01 | 2022-02-01 | open | bar: 3; 10; 2
3 | Steerer vertical | pbar Steerer v | 2021-03-01 | 2022-02-01 | open | bar: 3; 10; 2
1 | Steerer vertical radiation hard |  | 2022-01-01 | 2022-01-01 | open | bar: 1
8 | CR-type NC quad. wide | pbar quad wide | 2021-07-01 | 2021-12-01 | open |  | 7: 1; 8: 2; 9: 1; 10: 1; 11: 2; 12: 1
120 | pbar Vacuum | [5 empty] | 7: 1; 8: 2; 9: 1; 10: 1; 11: 2; 12: 1; 5: 112
8 | Chamber quadrupole wide | pbar quad wide | 2021-07-01 | 2021-12-01 | open |  | 7: 1; 8: 2; 9: 1; 10: 1; 11: 2; 12: 1
4 | Sextupole Chambers | pbar Sextupole | 2022-05-01 | 2022-05-01 | open |  | 5: 4
3 | p-Bar Horiz. Correctors | pbar Steerer h | 2022-05-01 | 2022-05-01 | open |  | 5: 3
3 | Vertical Correctors | pbar Steerer v | 2022-05-01 | 2022-05-01 | open |  | 5: 3
102 | Pumps/Valves/Roughing Stations/Adaptors/Support Frames |  | 2022-11-01 | 2022-11-01 | open |  | 5: 102
23 | pbar Power Converter | [5 empty] | 10: 7; 11: 4; 3: 1; 6: 6; 12: 5
1 | Dipole Power Converter |  | 2022-03-01 | 2022-03-01 | open | bar: 3
9 | Wide Quadrupole pulsed mode (1 radiation hard) |  | 2022-06-01 | 2022-12-01 | open |  | 6: 4; 12: 5
2 | narrow Quadrupole pulsed mode |  | 2022-06-01 | 2022-06-01 | open |  | 6: 2
4 | Sextupole Power Converter |  | 2021-11-01 | 2021-11-01 | open |  | 11: 4
7 | Steerer Power Converter |  | 2021-10-01 | 2021-10-01 | open |  | 10: 7
3 | pbar Collimators | [5 empty] | 3: 0
1 | p-Bar Horizontal beam resistant atm. mov. collimators |  | 2021-03-01 | 2021-03-01 | open | bar: 1
1 | p-Bar Vertical beam resistant atm. mov. collimators |  | 2021-03-01 | 2021-03-01 | open | bar: 1
1 | p-Bar Horizontal vacuum capable mov. collimators |  | 2021-03-01 | 2021-03-01 | open | bar: 1
193 | Super-FRS | [5 empty] | 2: 1; 4: 1; 4: 2; 8: 2; 11: 20; 12: 1; 2: 2; 3: 4; 4: 20; 5: 133; 6: 2; 7: 1; 9: 1; 10: 3
7 | Super-FRS Magnets | bar: 4; 8; 2 to 3; 5 to 6; 10
1 | Dipole 1.2 | SFRS dip | 2022-03-01 | 2022-03-01 | signed | bar: 3
1 | Dipole 1.3 | SFRS dip | 2022-05-01 | 2022-05-01 | signed | bar: 5
2 | NC Quadrupole 1 | SFRS NC Multipole | 2021-04-01 | 2021-08-01 | R&D | bar: 4; 8
1 | NC Quadrupole 2 | SFRS NC Multipole | 2022-02-01 | 2022-02-01 | R&D | bar: 2
2 | NC Sextupole | SFRS NC Multipole | 2022-06-01 | 2022-10-01 | R&D | bar: 6; 10
181 | Super-FRS Vacuum | [5 empty] | 2: 1; 4: 1; 4: 1; 8: 1; 11: 20; 2: 1; 3: 3; 4: 20; 5: 131; 6: 1; 10: 1
3 | NC dipole chambers | SFRS dip | 2022-03-01 | 2022-03-01 | open (EOI+R&D) |  | 3: 3
21 | SC Standard-Dipole Chambers |  | 2022-04-01 | 2022-04-01 | signed |  | 4: 1; 2: 20
5 | NC multipoles chambers | SFRS NC Multipole | 2022-05-01 | 2022-05-01 | open (EOI) | bar: 4; 8; 2; 6; 10
21 | Diagnostic Cambers |  | 2021-11-01 | 2021-11-01 | signed |  | 2: 1; 9: 20
3 | Branched dipole chamber |  | 2022-04-01 | 2022-04-01 | open (EOI) |  | 5: 3
128 | Beam pipes/bellows/pumping chambers |  | 2022-05-01 | 2022-05-01 | not assigned |  | 5: 128
1 | Super-FRS Beam Instrumentation | bar: 5
1 | BPM (CR-Branch) |  | 2022-05-01 | 2022-05-01 | not assigned | bar: 5
4 | Super-FRS Local Cryogenics | bar: 12; 7; 9 to 10
1 | Branch box |  | 2022-07-01 | 2022-07-01 | open (EOI) | bar: 7
1 | Warm piping |  | 2021-12-01 | 2021-12-01 | open (EOI) | bar: 12
1 | Transfer lines |  | 2022-09-01 | 2022-12-01 | open (EOI) | bar: 9 to 12
1 | Installation local cryogenics |  | 2022-10-01 | 2023-01-01 | open (EOI) | bar: 10 to 1
1 | HESR | bar: 1
1 | PANDA Dipole Magnet |  | 2022-01-01 | 2022-01-01 | signed | bar: 1
1 | PANDA | bar: 2
1 | Solenoid |  | 2022-02-01 | 2022-02-01 | signed | bar: 2
1 | CBM | bar: 10
1 | S.c. Dipole Magnet |  | 2022-10-01 | 2022-10-01 | signed | bar: 10
2834 | Components total |  |  |  |  | 27 | 122 | 24 | 24 | 1 | 25 | 3 | 17 | 73 | 11 | 117 | 26 | 243 | 25 | 18 | 127 | 20 | 36 | 38 | 19 | 24 | 25 | 1204 | 86 | 26 | 18 | 16 | 19 | 31 | 264 | 29 | 19 | 16 | 7 | 9 | 7 | 8 | 4 | 4 | 3 | 2 | 7 | 4 | 1 | 4 | 1
Data date 15.11.2019

## Action Items
Action Items
Discuss during BINP workshop
Contract negotiations | Latest delivery date assumption by work package leader, scheduling coordination between FAIR/GSI and BINP is needed.
Production scheduling | Delay of 122 HEBT magnets. New information about the production status is needed.
In-kind contracts between FAIR/GSI and BINP contain the latest delivery date of production lots, a detailed schedule of intermediate deliveries must be discussed.
The delivery of magnets and the associated vacuum chamber should be coordinated with each other. Optimal case when the vacuum chamber arrives at GSI at the same time, or shortly before the magnet.
Production scope and capacity must be cross checked.
Vacuum standard components | Some of the vacuum standard components from BINP like valves, gauges and pumps will be procured by FAIR for all machines. We have to clearify wich components in detail.

## Magnets
Delivery Matrix
BINP Magnets
|  |  | contract open | [5 empty] | To be discussed |  |  | Latest delivery date from contract, detailed production scheduling is needed.
|  | Latest delivery date assumption by WPL, scheduling coordination between FAIR/GSI and BINP is needed. | [6 empty] | To be discussed |  |  | Components delayed according to latest BINP production plan.
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Quantity | Work Package | Start delivery | Finish delivery | Contract status | delivered | 1: 2020; Components delayed according to latest BINP production plan. 1: 2021; Components delayed according to latest BINP production plan. 1: 2022; Components delayed according to latest BINP production plan. 1: 2023
310 | HEBT |  |  |  | 27 | 1: 122; 2: 23; 3: 8; To be discussed 5: 25; To be discussed 6: 2; Components delayed according to latest BINP production plan. 7: 8; Components delayed according to latest BINP production plan. 8: 8; Components delayed according to latest BINP production plan. 9: 8; Components delayed according to latest BINP production plan. 10: 15; Components delayed according to latest BINP production plan. 11: 12; Components delayed according to latest BINP production plan. 12: 10; Components delayed according to latest BINP production plan. 2: 8; Components delayed according to latest BINP production plan. 4: 4; Components delayed according to latest BINP production plan. 6: 23; Components delayed according to latest BINP production plan. 12: 7
310 | HEBT Magnets |  |  |  | 27 | 1: 122; 2: 23; 3: 8; To be discussed 5: 25; To be discussed 6: 2; Components delayed according to latest BINP production plan. 7: 8; Components delayed according to latest BINP production plan. 8: 8; Components delayed according to latest BINP production plan. 9: 8; Components delayed according to latest BINP production plan. 10: 15; Components delayed according to latest BINP production plan. 11: 12; Components delayed according to latest BINP production plan. 12: 10; Components delayed according to latest BINP production plan. 2: 8; Components delayed according to latest BINP production plan. 4: 4; Components delayed according to latest BINP production plan. 6: 23; Components delayed according to latest BINP production plan. 12: 7
6 | Dipole 10 (HEBT 100 Divider) - dip10 | 2019-08-01 | 01/20 | signed |  | 1: 6
4 | Dipole 15 (HEBT18) - dip15_0 | 2019-09-01 | 2019-09-01 | signed | 4
1 | Dipole 15 (HEBT18) - dip15_1 | 2019-07-01 | 2020-01-01 | signed | bar: 1
1 | Dipole 16 (HEBT18) - dip16 | 2019-07-01 | 2020-01-01 | signed | bar: 1
1 | Dipole 17 (HEBT18) - dip17_0 | 2019-09-01 | 2020-01-01 | signed | bar: 1
4 | Dipole 19 (HEBT100) - dip19_0 | 2019-09-01 | 2020-02-01 | signed |  | 1: 3; 2: 1
2 | Dipole 13 (SIS100) - dip13_0 | 2019-08-01 | 2020-01-01 | signed |  | 1: 2
3 | Dipole 13 (SIS100) - dip13_3 | 2019-11-01 | 2020-01-01 | signed |  | 1: 3
2 | Dipole 4 - dip4 FBL | 2021-06-01 | 2021-06-01 | signed |  | Components delayed according to latest BINP production plan. 4: 2
2 | CR-type dip3_3 | 2021-12-01 | 2021-12-01 | open |  | Components delayed according to latest BINP production plan. 10: 2
81 | Quadrupole 2 (SIS18 HEBT-Type long) | 2018-11-01 | 2020-12-01 | signed | 17 | 1: 35; 2: 7; Components delayed according to latest BINP production plan. 8: 8; Components delayed according to latest BINP production plan. 10: 7; Components delayed according to latest BINP production plan. 12: 7
4 | Quadrupole 10 (CBM Target-Focus Type long) | 2019-07-01 | 2020-01-01 | signed |  | 1: 4
69 | Quadrupole 11 (HEBT100) | 2019-07-01 | 2021-04-01 | signed |  | 1: 25; To be discussed 5: 8; Components delayed according to latest BINP production plan. 7: 8; Components delayed according to latest BINP production plan. 10: 8; Components delayed according to latest BINP production plan. 11: 8; Components delayed according to latest BINP production plan. 2: 8; Components delayed according to latest BINP production plan. 4: 4
12 | Quadrupole 12 (HEBT100) | 2019-11-01 | 2020-05-01 | signed |  | 1: 5; 3: 4; To be discussed 5: 3
1 | Quadrupole 1 FBL | 2021-06-01 | 2021-06-01 | signed | bar: Components delayed according to latest BINP production plan. 4 to Components delayed according to latest BINP production plan. 6
9 | Quadrupole 2 FBL | 2021-06-01 | 2021-06-01 | signed |  | Components delayed according to latest BINP production plan. 4: 9
4 | Quadrupole 2 (SIS18 HEBT-Type long) HED | 2021-06-01 | 2021-06-01 | signed |  | Components delayed according to latest BINP production plan. 4: 4
1 | Quadrupole 11 (HEBT100) HED | 2021-06-01 | 2021-06-01 | signed | bar: Components delayed according to latest BINP production plan. 4 to Components delayed according to latest BINP production plan. 6
5 | CR-type quad3_3 | 2021-12-01 | 2021-12-01 | open |  | Components delayed according to latest BINP production plan. 10: 5
5 | Steering Magnets HEBT18 (large aperture) | 2020-05-01 | 2020-09-01 | signed |  | To be discussed 5: 1; Components delayed according to latest BINP production plan. 9: 4
44 | Steering Magnets HEBT18 | 2019-06-01 | 2020-12-01 | signed | 2 | 1: 18; 2: 4; 3: 4; To be discussed 5: 3; To be discussed 6: 2; Components delayed according to latest BINP production plan. 9: 4; Components delayed according to latest BINP production plan. 11: 4; Components delayed according to latest BINP production plan. 12: 3
43 | Steering Magnets HEBT100 | 2019-06-01 | 2020-05-01 | signed | 4 | 1: 18; 2: 11; To be discussed 5: 10
2 | Steering Magnet HEBT100 HED | 2021-06-01 | 2021-06-01 | signed |  | Components delayed according to latest BINP production plan. 4: 2
4 | Steering Magnet HEBT18 FBL | 2021-06-01 | 2021-06-01 | signed |  | Components delayed according to latest BINP production plan. 4: 4
140 | CR | [10 empty] | 1 |  |  | 1 |  | 1 | 3 | 2 | 5 | 4 | 3 | 5 | 3 | 4 | 8 | 6 | 5 | 6 | 6 | 4 | 5 | 5 | 6 | 5 | 5 | 5 | 4 | 3 | 5 | 3 | 2 | 3 | 3 | 2 | 7 | 4 | 1 | 4 | 1
140 | CR Magnets | [10 empty] | 1 |  |  | 1 |  | 1 | 3 | 2 | 5 | 4 | 3 | 5 | 3 | 4 | 8 | 6 | 5 | 6 | 6 | 4 | 5 | 5 | 6 | 5 | 5 | 5 | 4 | 3 | 5 | 3 | 2 | 3 | 3 | 2 | 7 | 4 | 1 | 4 | 1
26 | CR/TCR1 Dipole Magnet | 2020-07-01 | 2023-08-01 | signed |  | Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 8: 2
29 | CR Wide Quadrupoles | 2020-10-01 | 2023-08-01 | signed |  | Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1
5 | TCR1 Wide Quadrupoles | 2023-05-01 | 2023-06-01 | signed |  | Components delayed according to latest BINP production plan. 5: 3; Components delayed according to latest BINP production plan. 6: 2
11 | CR Narrow Quadrupoles | 2020-12-01 | 2023-09-01 | signed | bar: Components delayed according to latest BINP production plan. 12; Components delayed according to latest BINP production plan. 2; Components delayed according to latest BINP production plan. 5; Components delayed according to latest BINP production plan. 9; Components delayed according to latest BINP production plan. 1; Components delayed according to latest BINP production plan. 5; Components delayed according to latest BINP production plan. 9; Components delayed according to latest BINP production plan. 1; Components delayed according to latest BINP production plan. 5; Components delayed according to latest BINP production plan. 8 to Components delayed according to latest BINP production plan. 9
1 | TCR1 Narrow Septum Quadrupole | 2021-10-01 | 2021-10-01 | signed | bar: Components delayed according to latest BINP production plan. 10
26 | CR/TCR1 Sextupole Magnets | 2021-04-01 | 2023-05-01 | signed | bar: Components delayed according to latest BINP production plan. 4 to Components delayed according to latest BINP production plan. 5
12 | CR Octupole Correctors | 2021-09-01 | 2022-07-01 | signed |  | Components delayed according to latest BINP production plan. 9: 2; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 1
3 | CR Injection Septum | 2021-11-01 | 2022-11-01 | signed |  | Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 11: 2
1 | CR Extr. Septum magnet | 2022-08-01 | 2022-08-01 | signed | bar: Components delayed according to latest BINP production plan. 8
4 | CR Combined Steering Magnets | 2021-04-01 | 2021-12-01 | signed | bar: Components delayed according to latest BINP production plan. 4; Components delayed according to latest BINP production plan. 6; Components delayed according to latest BINP production plan. 9; Components delayed according to latest BINP production plan. 12
21 | CR/TCR1 Vertical Steering Magnets | 2021-01-01 | 2022-09-01 | signed |  | Components delayed according to latest BINP production plan. 1: 2; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 9: 1
1 | TCR1 Combined Steering Magnets | 2022-03-01 | 2022-03-01 | signed | bar: Components delayed according to latest BINP production plan. 3
23 | pbar |  |  |  |  | Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 2; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 5; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 2; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 4
23 | pbar Magnets |  |  |  |  | Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 2; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 5; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 2; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 4
1 | Bending Magnet | 2022-04-01 | 2022-04-01 | open | bar: Components delayed according to latest BINP production plan. 4
2 | CR-type narrow quad. Radiation hard | 2021-10-01 | 2022-03-01 | open | bar: Components delayed according to latest BINP production plan. 10; Components delayed according to latest BINP production plan. 3
1 | Wide quad. Radiation hard | 2021-10-01 | 2021-10-01 | open | bar: Components delayed according to latest BINP production plan. 10
4 | Sextupole wide | 2022-05-01 | 2022-05-01 | open |  | Components delayed according to latest BINP production plan. 5: 4
3 | Steerer horizontal | 2021-03-01 | 2022-02-01 | open | bar: Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 10; Components delayed according to latest BINP production plan. 2
3 | Steerer vertical | 2021-03-01 | 2022-02-01 | open | bar: Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 10; Components delayed according to latest BINP production plan. 2
1 | Steerer vertical radiation hard | 2022-01-01 | 2022-01-01 | open | bar: Components delayed according to latest BINP production plan. 1
8 | CR-type NC quad. wide | 2021-07-01 | 2021-12-01 | open |  | Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 2; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 1
7 | Super-FRS | bar: Components delayed according to latest BINP production plan. 4; Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 2 to Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 5 to Components delayed according to latest BINP production plan. 6; Components delayed according to latest BINP production plan. 10
7 | Super-FRS Magnets | bar: Components delayed according to latest BINP production plan. 4; Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 2 to Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 5 to Components delayed according to latest BINP production plan. 6; Components delayed according to latest BINP production plan. 10
1 | Dipole 1.2 | 2022-03-01 | 2022-03-01 | signed | bar: Components delayed according to latest BINP production plan. 3
1 | Dipole 1.3 | 2022-05-01 | 2022-05-01 | signed | bar: Components delayed according to latest BINP production plan. 5
2 | NC Quadrupole 1 | 2021-04-01 | 2021-08-01 | R&D | bar: Components delayed according to latest BINP production plan. 4; Components delayed according to latest BINP production plan. 8
1 | NC Quadrupole 2 | 2022-02-01 | 2022-02-01 | R&D | bar: Components delayed according to latest BINP production plan. 2
2 | NC Sextupole | 2022-06-01 | 2022-10-01 | R&D | bar: Components delayed according to latest BINP production plan. 6; Components delayed according to latest BINP production plan. 10
1 | HESR | bar: Components delayed according to latest BINP production plan. 1
1 | PANDA Dipole Magnet | 2022-01-01 | 2022-01-01 | signed | bar: Components delayed according to latest BINP production plan. 1
1 | PANDA | bar: Components delayed according to latest BINP production plan. 2
1 | Solenoid | 2022-02-01 | 2022-02-01 | signed | bar: Components delayed according to latest BINP production plan. 2
1 | CBM | bar: Components delayed according to latest BINP production plan. 10
1 | S.c. Dipole Magnet | 2022-10-01 | 2022-10-01 | signed | bar: Components delayed according to latest BINP production plan. 10
483 | Magnets total |  |  |  | 27 | 122 | 23 | 8 |  | 25 | 2 | 9 | 8 | 8 | 16 | 12 | 11 | 3 | 10 | 7 | 9 | 3 | 28 | 4 | 7 | 9 | 11 | 7 | 14 | 8 | 8 | 7 | 6 | 11 | 6 | 5 | 5 | 4 | 5 | 5 | 3 | 2 | 3 | 3 | 2 | 7 | 4 | 1 | 4 | 1

## Vacuum
Delivery Matrix
BINP Vacuum components
|  |  | contract open | [5 empty] | To be discussed |  |  | Latest delivery date from contract, detailed production scheduling is needed.
|  | Latest delivery date assumption by WPL, scheduling coordination between FAIR/GSI and BINP is needed. | [6 empty] | To be discussed |  |  | Components delayed according to latest BINP production plan.
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Quantity | Work Package | Start delivery | Finish delivery | Contract status | delivered | 1: 2020; Components delayed according to latest BINP production plan. 1: 2021; Components delayed according to latest BINP production plan. 1: 2022; Components delayed according to latest BINP production plan. 1: 2023
1461 | HEBT |  |  |  |  | 3: 16; Components delayed according to latest BINP production plan. 7: 4; Components delayed according to latest BINP production plan. 8: 65; Components delayed according to latest BINP production plan. 10: 96; Components delayed according to latest BINP production plan. 11: 6; Components delayed according to latest BINP production plan. 1: 4; Components delayed according to latest BINP production plan. 3: 95; Components delayed according to latest BINP production plan. 10: 1175
1461 | HEBT Vacuum |  |  |  |  | 3: 16; Components delayed according to latest BINP production plan. 7: 4; Components delayed according to latest BINP production plan. 8: 65; Components delayed according to latest BINP production plan. 10: 96; Components delayed according to latest BINP production plan. 11: 6; Components delayed according to latest BINP production plan. 1: 4; Components delayed according to latest BINP production plan. 3: 95; Components delayed according to latest BINP production plan. 10: 1175
6 | Dipole chamber dip 10 Divider | 2020-11-01 | 2020-11-01 | signed |  | Components delayed according to latest BINP production plan. 9: 6
5 | Dipole chamber dip 13 | 2020-03-01 | 2020-03-01 | signed |  | 1: 5
5 | Dipole chanber dip 15 | 2020-03-01 | 2020-03-01 | signed |  | 1: 5
1 | Dipole chamber dip 16 | 2020-03-01 | 2020-03-01 | signed | bar: 3
1 | Dipole chamber dip 17 | 2020-03-01 | 2020-03-01 | signed | bar: 3
4 | Dipole chamber dip 19 | 2020-07-01 | 2020-07-01 | signed |  | To be discussed 5: 4
1 | Dipole chamber dip 4 (bending) FBL | 2021-03-01 | 2021-03-01 | signed | bar: Components delayed according to latest BINP production plan. 3
1 | Dipole chamber dip 4 (branching) FBL | 2021-03-01 | 2021-03-01 | signed | bar: Components delayed according to latest BINP production plan. 3
2 | CR-Type Dipole Chamber dip3_3 | 2021-03-01 | 2021-03-01 | open |  | Components delayed according to latest BINP production plan. 2: 2
4 | Quadrupole chamber quad10 | 2020-03-01 | 2020-03-01 | signed |  | 1: 4
69 | Quadrupole chamber quad 11 | 2021-03-01 | 2021-03-01 | signed |  | Components delayed according to latest BINP production plan. 1: 69
17 | Quadrupole chamber quad 12 | 2021-03-01 | 2021-03-01 | signed |  | Components delayed according to latest BINP production plan. 1: 17
81 | Quadrupole chamber quad 2 | 2020-10-01 | 2020-10-01 | signed |  | Components delayed according to latest BINP production plan. 8: 81
9 | Quadrupole chamber quad 2 FBL | 2020-10-01 | 2020-10-01 | signed |  | Components delayed according to latest BINP production plan. 8: 9
1 | Quadrupole Chamber quad1 FBL | 2020-10-01 | 2020-10-01 | signed | bar: Components delayed according to latest BINP production plan. 10
4 | Quadrupole Chamber quad2 HED | 2020-10-01 | 2020-10-01 | not assigned |  | Components delayed according to latest BINP production plan. 8: 4
1 | Quadrupole Chamber quad11 HED | 2020-10-01 | 2020-10-01 | not assigned | bar: Components delayed according to latest BINP production plan. 10
5 | CR-Type Quadrupole Chamber quad3_3 | 2021-03-01 | 2021-03-01 | open |  | Components delayed according to latest BINP production plan. 1: 5
29 | Steerer chamber s100 | 2020-08-01 | 2020-08-01 | signed |  | To be discussed 6: 29
2 | Steerer Chambers s100 HED | 2020-08-01 | 2020-08-01 | not assigned |  | Components delayed according to latest BINP production plan. 7: 2
31 | Steerer chamber s18h/v | 2020-08-01 | 2020-08-01 | signed |  | To be discussed 6: 31
3 | Steerer chamber s18h/v FBL | 2020-08-01 | 2020-08-01 | signed |  | To be discussed 6: 3
4 | Steerer chamber s13 large aperture | 2021-01-01 | 2021-01-01 | signed |  | Components delayed according to latest BINP production plan. 11: 4
1175 | Batch 4 (Bellows, Pumping Chambers, Straight Tubes) | 2021-10-01 | 2021-10-01 | open |  | Components delayed according to latest BINP production plan. 8: 1175
415 | CR |  |  |  |  | Components delayed according to latest BINP production plan. 7: 3; Components delayed according to latest BINP production plan. 9: 2; Components delayed according to latest BINP production plan. 10: 4; Components delayed according to latest BINP production plan. 11: 6; Components delayed according to latest BINP production plan. 12: 229; Components delayed according to latest BINP production plan. 1: 14; Components delayed according to latest BINP production plan. 2: 5; Components delayed according to latest BINP production plan. 3: 21; Components delayed according to latest BINP production plan. 4: 8; Components delayed according to latest BINP production plan. 5: 30; Components delayed according to latest BINP production plan. 6: 7; Components delayed according to latest BINP production plan. 7: 8; Components delayed according to latest BINP production plan. 8: 8; Components delayed according to latest BINP production plan. 9: 7; Components delayed according to latest BINP production plan. 10: 5; Components delayed according to latest BINP production plan. 11: 48; Components delayed according to latest BINP production plan. 12: 6; Components delayed according to latest BINP production plan. 1: 4
415 | CR Vacuum |  |  |  |  | Components delayed according to latest BINP production plan. 7: 3; Components delayed according to latest BINP production plan. 9: 2; Components delayed according to latest BINP production plan. 10: 4; Components delayed according to latest BINP production plan. 11: 6; Components delayed according to latest BINP production plan. 12: 229; Components delayed according to latest BINP production plan. 1: 14; Components delayed according to latest BINP production plan. 2: 5; Components delayed according to latest BINP production plan. 3: 21; Components delayed according to latest BINP production plan. 4: 8; Components delayed according to latest BINP production plan. 5: 30; Components delayed according to latest BINP production plan. 6: 7; Components delayed according to latest BINP production plan. 7: 8; Components delayed according to latest BINP production plan. 8: 8; Components delayed according to latest BINP production plan. 9: 7; Components delayed according to latest BINP production plan. 10: 5; Components delayed according to latest BINP production plan. 11: 48; Components delayed according to latest BINP production plan. 12: 6; Components delayed according to latest BINP production plan. 1: 4
24 | CR Dipole Chamber | 2020-07-01 | 2022-01-01 | signed |  | Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 2; Components delayed according to latest BINP production plan. 1: 2; Components delayed according to latest BINP production plan. 5: 2; Components delayed according to latest BINP production plan. 6: 3; Components delayed according to latest BINP production plan. 7: 3; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 4; Components delayed according to latest BINP production plan. 1: 3
2 | TCR1 Dipole Chamber | 2021-10-01 | 2021-12-01 | signed | bar: Components delayed according to latest BINP production plan. 10; Components delayed according to latest BINP production plan. 12
29 | CR Wide Quad+Sext Chamber | 2020-07-01 | 2021-11-01 | signed |  | Components delayed according to latest BINP production plan. 7: 2; Components delayed according to latest BINP production plan. 9: 2; Components delayed according to latest BINP production plan. 10: 4; Components delayed according to latest BINP production plan. 11: 3; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 4; Components delayed according to latest BINP production plan. 5: 3; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 2; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 3; Components delayed according to latest BINP production plan. 11: 1
6 | TCR1 Wide Quadrupole Chamber | 2021-08-01 | 2021-09-01 | signed |  | Components delayed according to latest BINP production plan. 8: 4; Components delayed according to latest BINP production plan. 9: 2
43 | Straight Tubes | 2020-11-01 | 2021-09-01 | signed |  | Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 2; Components delayed according to latest BINP production plan. 1: 8; Components delayed according to latest BINP production plan. 2: 5; Components delayed according to latest BINP production plan. 3: 4; Components delayed according to latest BINP production plan. 4: 4; Components delayed according to latest BINP production plan. 5: 2; Components delayed according to latest BINP production plan. 6: 3; Components delayed according to latest BINP production plan. 7: 3; Components delayed according to latest BINP production plan. 8: 2; Components delayed according to latest BINP production plan. 9: 4; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 1
311 | Pumps/Valves/Roughing Stations/Adaptors/Support Frames | 2020-12-01 | 2021-11-01 | signed |  | Components delayed according to latest BINP production plan. 12: 225; Components delayed according to latest BINP production plan. 1: 4; Components delayed according to latest BINP production plan. 3: 15; Components delayed according to latest BINP production plan. 5: 23; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 11: 43
120 | pbar |  |  |  |  | Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 2; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 5: 112
120 | pbar Vacuum |  |  |  |  | Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 2; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 5: 112
8 | Chamber quadrupole wide | 2021-07-01 | 2021-12-01 | open |  | Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 2; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 2; Components delayed according to latest BINP production plan. 12: 1
4 | Sextupole Chambers | 2022-05-01 | 2022-05-01 | open |  | Components delayed according to latest BINP production plan. 5: 4
3 | p-Bar Horiz. Correctors | 2022-05-01 | 2022-05-01 | open |  | Components delayed according to latest BINP production plan. 5: 3
3 | Vertical Correctors | 2022-05-01 | 2022-05-01 | open |  | Components delayed according to latest BINP production plan. 5: 3
102 | Pumps/Valves/Roughing Stations/Adaptors/Support Frames | 2022-11-01 | 2022-11-01 | open |  | Components delayed according to latest BINP production plan. 5: 102
181 | Super-FRS |  |  |  |  | 2: 1; To be discussed 4: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 11: 20; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 3; Components delayed according to latest BINP production plan. 4: 20; Components delayed according to latest BINP production plan. 5: 131; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 10: 1
181 | Super-FRS Vacuum |  |  |  |  | 2: 1; To be discussed 4: 1; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 11: 20; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 3; Components delayed according to latest BINP production plan. 4: 20; Components delayed according to latest BINP production plan. 5: 131; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 10: 1
3 | NC dipole chambers | 2022-03-01 | 2022-03-01 | open (EOI+R&D) |  | Components delayed according to latest BINP production plan. 3: 3
21 | SC Standard-Dipole Chambers | 2022-04-01 | 2022-04-01 | signed |  | To be discussed 4: 1; Components delayed according to latest BINP production plan. 2: 20
5 | NC multipoles chambers | 2022-05-01 | 2022-05-01 | open (EOI) | bar: Components delayed according to latest BINP production plan. 4; Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 2; Components delayed according to latest BINP production plan. 6; Components delayed according to latest BINP production plan. 10
21 | Diagnostic Cambers | 2021-11-01 | 2021-11-01 | signed |  | 2: 1; Components delayed according to latest BINP production plan. 9: 20
3 | Branched dipole chamber | 2022-04-01 | 2022-04-01 | open (EOI) |  | Components delayed according to latest BINP production plan. 5: 3
128 | Beam pipes/bellows/pumping chambers | 2022-05-01 | 2022-05-01 | not assigned |  | Components delayed according to latest BINP production plan. 5: 128
2177 | Vacuum components total |  |  |  |  | 2: 1; 3: 16; To be discussed 4: 1; Components delayed according to latest BINP production plan. 7: 7; Components delayed according to latest BINP production plan. 8: 65; Components delayed according to latest BINP production plan. 9: 2; Components delayed according to latest BINP production plan. 10: 100; Components delayed according to latest BINP production plan. 11: 12; Components delayed according to latest BINP production plan. 12: 229; Components delayed according to latest BINP production plan. 1: 18; Components delayed according to latest BINP production plan. 2: 5; Components delayed according to latest BINP production plan. 3: 116; Components delayed according to latest BINP production plan. 4: 9; Components delayed according to latest BINP production plan. 5: 30; Components delayed according to latest BINP production plan. 6: 7; Components delayed according to latest BINP production plan. 7: 9; Components delayed according to latest BINP production plan. 8: 11; Components delayed according to latest BINP production plan. 9: 8; Components delayed according to latest BINP production plan. 10: 1181; Components delayed according to latest BINP production plan. 11: 70; Components delayed according to latest BINP production plan. 12: 7; Components delayed according to latest BINP production plan. 1: 4; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 3; Components delayed according to latest BINP production plan. 4: 20; Components delayed according to latest BINP production plan. 5: 243; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 10: 1

## Power Converter
Delivery Matrix
BINP Power Converter
|  |  | contract open | [5 empty] | To be discussed |  |  | Latest delivery date from contract, detailed production scheduling is needed.
|  | Latest delivery date assumption by WPL, scheduling coordination between FAIR/GSI and BINP is needed. | [6 empty] | To be discussed |  |  | Components delayed according to latest BINP production plan.
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Quantity | Work Package | Start delivery | Finish delivery | Contract status | delivered | 1: 2020; Components delayed according to latest BINP production plan. 1: 2021; Components delayed according to latest BINP production plan. 1: 2022; Components delayed according to latest BINP production plan. 1: 2023
103 | CR |  |  |  |  | Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 2; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 2; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 2; Components delayed according to latest BINP production plan. 6: 3; Components delayed according to latest BINP production plan. 7: 5; Components delayed according to latest BINP production plan. 8: 4; Components delayed according to latest BINP production plan. 9: 6; Components delayed according to latest BINP production plan. 10: 4; Components delayed according to latest BINP production plan. 11: 4; Components delayed according to latest BINP production plan. 12: 4; Components delayed according to latest BINP production plan. 1: 5; Components delayed according to latest BINP production plan. 2: 6; Components delayed according to latest BINP production plan. 3: 6; Components delayed according to latest BINP production plan. 4: 5; Components delayed according to latest BINP production plan. 5: 7; Components delayed according to latest BINP production plan. 6: 11; Components delayed according to latest BINP production plan. 7: 11; Components delayed according to latest BINP production plan. 8: 8; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1
103 | CR Power Converter |  |  |  |  | Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 2; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 2; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 2; Components delayed according to latest BINP production plan. 6: 3; Components delayed according to latest BINP production plan. 7: 5; Components delayed according to latest BINP production plan. 8: 4; Components delayed according to latest BINP production plan. 9: 6; Components delayed according to latest BINP production plan. 10: 4; Components delayed according to latest BINP production plan. 11: 4; Components delayed according to latest BINP production plan. 12: 4; Components delayed according to latest BINP production plan. 1: 5; Components delayed according to latest BINP production plan. 2: 6; Components delayed according to latest BINP production plan. 3: 6; Components delayed according to latest BINP production plan. 4: 5; Components delayed according to latest BINP production plan. 5: 7; Components delayed according to latest BINP production plan. 6: 11; Components delayed according to latest BINP production plan. 7: 11; Components delayed according to latest BINP production plan. 8: 8; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1
1 | CR Dipole Power Conveter | 2022-07-01 | 2022-07-01 | signed | bar: Components delayed according to latest BINP production plan. 7
2 | TCR1 Dipole Power Conveter | 2022-10-01 | 2022-11-01 | signed | bar: Components delayed according to latest BINP production plan. 10 to Components delayed according to latest BINP production plan. 11
15 | CR Quadrupole Power Conveter | 2021-06-01 | 2022-08-01 | signed |  | Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 5: 2; Components delayed according to latest BINP production plan. 6: 5; Components delayed according to latest BINP production plan. 7: 4; Components delayed according to latest BINP production plan. 8: 3
6 | TCR1 Quadrupole Power Conveter | 2021-09-01 | 2022-08-01 | signed | bar: Components delayed according to latest BINP production plan. 9; Components delayed according to latest BINP production plan. 4 to Components delayed according to latest BINP production plan. 8
6 | CR Sextupole Power Conveter | 2021-05-01 | 2022-09-01 | signed | bar: Components delayed according to latest BINP production plan. 5; Components delayed according to latest BINP production plan. 5 to Components delayed according to latest BINP production plan. 9
2 | TCR1 Sextupole Power Conveter | 2022-02-01 | 2022-03-01 | signed | bar: Components delayed according to latest BINP production plan. 2 to Components delayed according to latest BINP production plan. 3
48 | CR Steering Magnet Power Conveter | 2020-12-01 | 2022-08-01 | signed |  | Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 6: 1; Components delayed according to latest BINP production plan. 7: 4; Components delayed according to latest BINP production plan. 8: 3; Components delayed according to latest BINP production plan. 9: 4; Components delayed according to latest BINP production plan. 10: 3; Components delayed according to latest BINP production plan. 11: 3; Components delayed according to latest BINP production plan. 12: 3; Components delayed according to latest BINP production plan. 1: 3; Components delayed according to latest BINP production plan. 2: 3; Components delayed according to latest BINP production plan. 3: 4; Components delayed according to latest BINP production plan. 4: 3; Components delayed according to latest BINP production plan. 5: 3; Components delayed according to latest BINP production plan. 6: 4; Components delayed according to latest BINP production plan. 7: 3; Components delayed according to latest BINP production plan. 8: 3
7 | TCR1 Steering Magnet Power Conveter | 2021-02-01 | 2022-03-01 | signed |  | Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 2; Components delayed according to latest BINP production plan. 2: 2; Components delayed according to latest BINP production plan. 3: 1
12 | CR Octupole Power Conveter | 2020-11-01 | 2021-10-01 | signed | bar: Components delayed according to latest BINP production plan. 11 to Components delayed according to latest BINP production plan. 10
4 | CR Injection/Extraction Power Conveter | 2021-03-01 | 2022-07-01 | signed | bar: Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 11; Components delayed according to latest BINP production plan. 4; Components delayed according to latest BINP production plan. 7
23 | pbar |  |  |  |  | Components delayed according to latest BINP production plan. 10: 7; Components delayed according to latest BINP production plan. 11: 4; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 6: 6; Components delayed according to latest BINP production plan. 12: 5
23 | pbar Power Converter |  |  |  |  | Components delayed according to latest BINP production plan. 10: 7; Components delayed according to latest BINP production plan. 11: 4; Components delayed according to latest BINP production plan. 3: 1; Components delayed according to latest BINP production plan. 6: 6; Components delayed according to latest BINP production plan. 12: 5
1 | Dipole Power Converter | 2022-03-01 | 2022-03-01 | open | bar: Components delayed according to latest BINP production plan. 3
9 | Wide Quadrupole pulsed mode (1 radiation hard) | 2022-06-01 | 2022-12-01 | open |  | Components delayed according to latest BINP production plan. 6: 4; Components delayed according to latest BINP production plan. 12: 5
2 | narrow Quadrupole pulsed mode | 2022-06-01 | 2022-06-01 | open |  | Components delayed according to latest BINP production plan. 6: 2
4 | Sextupole Power Converter | 2021-11-01 | 2021-11-01 | open |  | Components delayed according to latest BINP production plan. 11: 4
7 | Steerer Power Converter | 2021-10-01 | 2021-10-01 | open |  | Components delayed according to latest BINP production plan. 10: 7
126 | Power Converter total |  |  |  |  | Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 2; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 2; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 2; Components delayed according to latest BINP production plan. 6: 3; Components delayed according to latest BINP production plan. 7: 5; Components delayed according to latest BINP production plan. 8: 4; Components delayed according to latest BINP production plan. 9: 6; Components delayed according to latest BINP production plan. 10: 11; Components delayed according to latest BINP production plan. 11: 8; Components delayed according to latest BINP production plan. 12: 4; Components delayed according to latest BINP production plan. 1: 5; Components delayed according to latest BINP production plan. 2: 6; Components delayed according to latest BINP production plan. 3: 7; Components delayed according to latest BINP production plan. 4: 5; Components delayed according to latest BINP production plan. 5: 7; Components delayed according to latest BINP production plan. 6: 17; Components delayed according to latest BINP production plan. 7: 11; Components delayed according to latest BINP production plan. 8: 8; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 5

## Beam Instrumentation
Delivery Matrix
BINP Beam Instrumentation
|  |  | contract open | [5 empty] | To be discussed |  |  | Latest delivery date from contract, detailed production scheduling is needed.
|  | Latest delivery date assumption by WPL, scheduling coordination between FAIR/GSI and BINP is needed. | [6 empty] | To be discussed |  |  | Components delayed according to latest BINP production plan.
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Quantity | Work Package | Start delivery | Finish delivery | Contract status | delivered | 1: 2020; Components delayed according to latest BINP production plan. 1: 2021; Components delayed according to latest BINP production plan. 1: 2022; Components delayed according to latest BINP production plan. 1: 2023
41 | CR |  |  |  |  | To be discussed 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 3; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 9: 2; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 5: 2; Components delayed according to latest BINP production plan. 6: 4; Components delayed according to latest BINP production plan. 7: 2; Components delayed according to latest BINP production plan. 8: 3; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 1: 2; Components delayed according to latest BINP production plan. 2: 1
41 | CR Beam Instrumentation |  |  |  |  | To be discussed 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 3; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 9: 2; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 5: 2; Components delayed according to latest BINP production plan. 6: 4; Components delayed according to latest BINP production plan. 7: 2; Components delayed according to latest BINP production plan. 8: 3; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 1: 2; Components delayed according to latest BINP production plan. 2: 1
1 | DC Transformer | 2021-10-01 | 2021-10-01 | signed | bar: Components delayed according to latest BINP production plan. 10
19 | CR Beam Postition Monitors | 2020-06-01 | 2023-02-01 | signed | bar: To be discussed 6 to Components delayed according to latest BINP production plan. 7; Components delayed according to latest BINP production plan. 9; Components delayed according to latest BINP production plan. 11; Components delayed according to latest BINP production plan. 1; Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 5; Components delayed according to latest BINP production plan. 7; Components delayed according to latest BINP production plan. 9; Components delayed according to latest BINP production plan. 11; Components delayed according to latest BINP production plan. 1; Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 5; Components delayed according to latest BINP production plan. 7 to Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 10 to Components delayed according to latest BINP production plan. 11; Components delayed according to latest BINP production plan. 1 to Components delayed according to latest BINP production plan. 2
3 | TCR1 Beam Position Monitors | 2022-06-01 | 2022-08-01 | signed | bar: Components delayed according to latest BINP production plan. 6 to Components delayed according to latest BINP production plan. 8
1 | CR Fast Current Transformer | 2020-10-01 | 2022-05-01 | signed | bar: Components delayed according to latest BINP production plan. 10
1 | TCR1 Fast Current Transformer | 2020-10-01 | 2022-05-01 | open | bar: Components delayed according to latest BINP production plan. 5
1 | CR Residual Gas Profile Monitor | 2022-06-01 | 2022-06-01 | signed | bar: Components delayed according to latest BINP production plan. 6
5 | CR Scintillation Screen | 2020-12-01 | 2022-08-01 | signed | bar: Components delayed according to latest BINP production plan. 12; Components delayed according to latest BINP production plan. 2; Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 2; Components delayed according to latest BINP production plan. 8
3 | TCR1 Scintillation Screen | 2021-04-01 | 2023-01-01 | open | bar: Components delayed according to latest BINP production plan. 4; Components delayed according to latest BINP production plan. 6; Components delayed according to latest BINP production plan. 1
2 | CR Beam Stopper | 2021-01-01 | 2022-06-01 | signed | bar: Components delayed according to latest BINP production plan. 1; Components delayed according to latest BINP production plan. 6
5 | CR Beam Scraper | 2021-01-01 | 2022-09-01 | signed | bar: Components delayed according to latest BINP production plan. 1; Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 9; Components delayed according to latest BINP production plan. 3; Components delayed according to latest BINP production plan. 9
1 | Super-FRS | bar: Components delayed according to latest BINP production plan. 5
1 | Super-FRS Beam Instrumentation | bar: Components delayed according to latest BINP production plan. 5
1 | BPM (CR-Branch) | 2022-05-01 | 2022-05-01 | not assigned | bar: Components delayed according to latest BINP production plan. 5
42 | Beam Instrumentation components total |  |  |  |  | To be discussed 6: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 12: 1; Components delayed according to latest BINP production plan. 1: 3; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 4: 1; Components delayed according to latest BINP production plan. 5: 1; Components delayed according to latest BINP production plan. 7: 1; Components delayed according to latest BINP production plan. 8: 1; Components delayed according to latest BINP production plan. 9: 2; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 1: 1; Components delayed according to latest BINP production plan. 2: 1; Components delayed according to latest BINP production plan. 3: 2; Components delayed according to latest BINP production plan. 5: 3; Components delayed according to latest BINP production plan. 6: 4; Components delayed according to latest BINP production plan. 7: 2; Components delayed according to latest BINP production plan. 8: 3; Components delayed according to latest BINP production plan. 9: 1; Components delayed according to latest BINP production plan. 10: 1; Components delayed according to latest BINP production plan. 11: 1; Components delayed according to latest BINP production plan. 1: 2; Components delayed according to latest BINP production plan. 2: 1

## Injection Extraction
Delivery Matrix
BINP Injection/Extraction
|  |  | contract open | [5 empty] | To be discussed |  |  | Latest delivery date from contract, detailed production scheduling is needed.
|  | Latest delivery date assumption by WPL, scheduling coordination between FAIR/GSI and BINP is needed. | [6 empty] | To be discussed |  |  | Components delayed according to latest BINP production plan.
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Quantity | Work Package | Start delivery | Finish delivery | Contract status | delivered | 1: 2020; Components delayed according to latest BINP production plan. 1: 2021; Components delayed according to latest BINP production plan. 1: 2022; Components delayed according to latest BINP production plan. 1: 2023
2 | CR | bar: Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 6
2 | CR Injection/Extraction | bar: Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 6
2 | Injection/Extraction Kickers | 2021-08-01 | 2022-06-01 | signed | bar: Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 6
2 | Components total | bar: Components delayed according to latest BINP production plan. 8; Components delayed according to latest BINP production plan. 6

## Special Installations
Delivery Matrix
BINP Special Installations
|  |  | contract open | [5 empty] | To be discussed |  |  | Latest delivery date from contract, detailed production scheduling is needed.
|  | Latest delivery date assumption by WPL, scheduling coordination between FAIR/GSI and BINP is needed. | [6 empty] | To be discussed |  |  | Components delayed according to latest BINP production plan.
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Quantity | Work Package | Start delivery | Finish delivery | Contract status | delivered | 1: 2020; Components delayed according to latest BINP production plan. 1: 2021; Components delayed according to latest BINP production plan. 1: 2022; Components delayed according to latest BINP production plan. 1: 2023
3 | pbar |  |  |  |  | Components delayed according to latest BINP production plan. 3: 3
3 | pbar Collimators |  |  |  |  | Components delayed according to latest BINP production plan. 3: 3
1 | p-Bar Horizontal beam resistant atm. mov. collimators | 2021-03-01 | 2021-03-01 | open | bar: Components delayed according to latest BINP production plan. 3
1 | p-Bar Vertical beam resistant atm. mov. collimators | 2021-03-01 | 2021-03-01 | open | bar: Components delayed according to latest BINP production plan. 3
1 | p-Bar Horizontal vacuum capable mov. collimators | 2021-03-01 | 2021-03-01 | open | bar: Components delayed according to latest BINP production plan. 3
3 | Components total |  |  |  |  | Components delayed according to latest BINP production plan. 3: 3

## Local Cryogenics
Delivery Matrix
BINP Local Cryogenics
|  |  | contract open | [5 empty] | To be discussed |  |  | Latest delivery date from contract, detailed production scheduling is needed.
|  | Latest delivery date assumption by WPL, scheduling coordination between FAIR/GSI and BINP is needed. | [6 empty] | To be discussed |  |  | Components delayed according to latest BINP production plan.
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Quantity | Work Package | Start delivery | Finish delivery | Contract status | delivered | 1: 2020; Components delayed according to latest BINP production plan. 1: 2021; Components delayed according to latest BINP production plan. 1: 2022; Components delayed according to latest BINP production plan. 1: 2023
4 | Super-FRS | bar: Components delayed according to latest BINP production plan. 12; Components delayed according to latest BINP production plan. 7; Components delayed according to latest BINP production plan. 10 to Components delayed according to latest BINP production plan. 11
4 | Super-FRS Local Cryogenics | bar: Components delayed according to latest BINP production plan. 12; Components delayed according to latest BINP production plan. 7; Components delayed according to latest BINP production plan. 10 to Components delayed according to latest BINP production plan. 11
1 | Branch box | 2022-07-01 | 2022-07-01 | open (EOI) | bar: Components delayed according to latest BINP production plan. 7
1 | Warm piping | 2021-12-01 | 2021-12-01 | open (EOI) | bar: Components delayed according to latest BINP production plan. 12
1 | Transfer lines | 2022-09-01 | 2022-12-01 | open (EOI) | bar: Components delayed according to latest BINP production plan. 9 to Components delayed according to latest BINP production plan. 12
1 | Installation local cryogenics | 2022-10-01 | 2023-01-01 | open (EOI) | bar: Components delayed according to latest BINP production plan. 10 to Components delayed according to latest BINP production plan. 1
4 | Components total | bar: Components delayed according to latest BINP production plan. 12; Components delayed according to latest BINP production plan. 7; Components delayed according to latest BINP production plan. 10 to Components delayed according to latest BINP production plan. 11