## Slide 1
Status of the PANDA Solenoid Magnet Production in BINP
S.Pivovarov, E.Pyata, BINP, Novosibirsk

## Slide 2
PANDA solenoid magnet, BINP responsibility
Figure 1. Arrangement of the components of the PANDA solenoid.
Power supply and energy extraction system
Cable channel
Control Dewar box
Solenoid and yoke
Frame of Yoke

## Slide 3
Development of the PANDA solenoid magnet
Name of item | Status of work
Yoke and frame | Design is ready, production
Cryostat of solenoid | Design is ready, technological development, Call for tender
Cold mass | Design is ready, technological development, Call for tender
Conductor purchasing | Development work, preparation Call for tender
Control Dewar box | Preliminary design December 2019
PANDA solenoid power cabling | Design is ready, production
Power supply and energy extraction system | Detail design is ready, production
Magnet safety system | in process
Table 2. Status of work of the PANDA solenoid production.

## Slide 4
The main milestones of the yoke production
Name of milestone | Date 2017/10
FDR of the yoke | 20-25/11/2017
Contract with SibMash (SET), signed | 2/11/2017
Purchasing raw materials (1st batch, 60 t) | 26/12/2017
Start of production of the 1st octant | 01/2018
Status production | 
First octant production, W3 | 11/2018
Welding of 8 octants | ready
Machining of 6 octants | ready
Final machining of the vertical octant | 11/2019
Final machining of the upper octant | 11/2019
Production of the Upstream door | 11/2019
Production of the Downstream door | 11/2019
Production of a tooling for the yoke assembly | 11/2019
Table 3. The main milestones of the yoke production.

## Slide 5
The main milestones of the yoke production
Name of milestone | Date 2017/10
Production of the all barrel octants | 11/2019
Production of the frame and beams | 11/2019
Production of the doors | 12/2019
Control assembling at SET | 12/2019
Finalization of the parts | 12/2019-01/2020
Assembling of the Yoke at BINP | ? Q2-2020
Table3. The main milestones of the yoke production.

## Slide 6
The main milestones of the Cryostat production
Name of milestone |  | Date 2017/10
FDR of the Cryostat |  | 08/02/2019
FDR of the Cold Mass |  | 17/04/2019
Status production |  | 
Cryostat | Design is ready, technological development, Call for tender | 
Cold Mass | Design is ready, technological development, Call for tender | 
First Prototype of the Coil | 11/2019 | 
Tooling for winding Coil (and Prototype) | 11/2019 | 
Tooling for impregnation of Coil (and Prototype) | 11/2019 | 
2nd and 3rd Prototype production | 12/2019 – 02/2020 | 
Tooling for assembling of the Magnet | Design is ready, technological development, Call for tender | 
Tooling for installation of the Magnet into the Yoke | Design is ready, technological development, Call for tender | 
Table 3. The main milestones of the Cryostat production.

## Slide 7
Status of the PANDA conductor development/ procurement

## Slide 8
Main risks
Figure 6. Longitudinal section of the cryostat with cold mass.
Figure 5. Cold mass cross-section.
Figure 9. Drawing of the conductor.
Table 7. Conductor mechanical and electrical parameters.
Thickness (after cold work) at 300 K | mm | 7.93 | ± 0.03
Width (after cold work) at 300 K | mm | 10.95 | ± 0.03
Critical current (at 4.2 K, 5 T) | A | > 14690 | 
Critical current (at 4.5 K, 3 T) | A | > 16750 | 
Overall Al/Cu/sc ratio |  | 10.5/1.0/1.0 | 
Aluminum RRR (at 4.2 K, 0 T) |  | > 1000 | 
Al 0.2% yield strength at 300 K | MPa | > 30 | 
Purchasing super conductive conductor - lack of a manufacturers
Rutherford cable, 8 strands, extruded in Al matrix

## Slide 9
Rutherford cable co-extrusion/ conklad in a pure Al
Plan
Production of new dies - July 2019 - ready.
Tests of the Conklad - July 2019. - ready
Cryogenic tests in CERN/ VNIIKP - December 2019/ February 2020
Request 1000m Cu Rutherford cable for tests in SARKO - preparation of the contract
Preparation contracts for PANDA NbTi strands production, VNIINM - 11-12/ 2019
Preparation contracts for PANDA Rutherford cables production, VNIIKP - 1-2/ 2020
1000m Cu Rutherford cable for tests in SARKO - 02-03/ 2020
Preparation contracts for PANDA conductor production with SARKO - 02-03/ 2020
Status of the PANDA conductor development/ procurement

## Slide 10
Rutherford cable co-extrusion/ conklad in a pure Al
Plan
Procurement A995/998 wire 9,5 mm
Preparation of the contract for purchasing 3500 kg A995 aluminum raw material;
Sign of the contract for production A995/998 wire Ø 9,5 mm with NANOELECTRO:
First step – production from A995 aluminum raw material 147 kg;
2nd step – production 2500 kg A995/998 wire 9,5 mm.
Conklad – 02/2020 in SARKO with prototype PANDA cable and A995/998 wire 9,5 mm.
Tests of the prototype PANDA cable and A995/998 matrix after Conklad – 02-03/2020
Co-extrusion/ Conklad – 02/2020 in SARKO with Cu Rutherford cable 1000m and A995/998 wire 9,5 mm.
Cold work to result the overall geometrical conductor dimensions - 03-04/ 2020
Production PANDA NbTi strands - 06-07/ 2020
Production PANDA NbTi conductor with A995 matrix - 07-08/ 2020
Status of the PANDA conductor development/ procurement

## Slide 11
Sarko.
Produced about 20 meters a conductor from A95 and NbTi cable;
4 pieces the conductor 3,5m prepared for following tests;
Mechanical tests should be in BINP;
Cryogenic tests for RRR and critical currents should be carried out in Bochvar institute and CERN.

## Slide 12: 3D model of the Yoke and Frame.
Control assembling 12/2019
Frame
Yoke

## Slide 13: Module production
Finished module
Module after welding

## Slide 14: Upstream Door production

## Slide 15: Downstream Door production

## Slide 16: Beam production

## Slide 17: Top Frame production

## Slide 18: Vertical Beams production

## Slide 19: Angle Beams production

## Slide 20: 3D model of the Magnet and Control Dewar.
Design is ready, technological development
Control Dewar box
Cryostat and Coil
Preliminary design December 2019

## Slide 21: The Prototype of the Coil (3pcs.)
d = 1m, L=180 mm
Conductor:
Al - 10,85 мм x 7.93 мм,
6 layers - 16 turns
.
Design is ready, production

## Slide 22: Drawing of the Devices for winding coil (scheme).
Design is ready, production

## Slide 23: Drawing of the Device for impregnation coil (scheme).
Design is ready, production

## Slide 24: Tooling for winding and impregnation coil of Prototype

## Slide 25
Tooling for assembling of PANDA Magnet
Beam
FPDSSM42010000AS_Aуфь
Support of outer shield
FPDSSM42020000AS_A
Support of cold mass
FPDSSM42030000AS_A
Support of inner shield
FPDSSM42040000AS_A
Support of inner shell of cryostat FPDSSM42050000AS_A
Support of flanges of cryostat
FPDSSM42060000AS_A
Design is ready, technological development

## Slide 26
Tooling for installation of the Magnet into the Yoke
Design is ready, technological development
Removable Support
Fixed Support
Beam (1.6t)
Central removable Support
Support for Magnet
Rollers system
Transport support
of Magnet

## Slide 27
Installation procedure of the Magnet into the Iron Yoke
Insert removable support and install the rollers system for moving magnet.
Rollers system

## Slide 28
Thank you for your attention