## Slide 1: “New and Improved”: The JLab (state-of-the-art) HCO System
Dr. Ken Baggett
Engineering Support Liaison to Operations
At least until the next guy talks…

## Slide 2: Outline
  Why change?
  Overview of JLAB’s new Hot Checkout (HCO) processS
  Process Execution
    Users
    Signoff processes
    Operations Utilization
  Summary

## Slide 3: Why Change?
On 10/14/12 two Septa magnets (YR) in the Northeast Spreader region caught on fire and sustained heavy damage.

## Slide 4: YR Fire - What went wrong? (cont.)
What happened?
  LCW valves for the dipoles were closed.
  A jumper in the box supply prevented the thermal switches from tripping the box supply on an over temperature fault.
Root causes identified to be:
  Lack of adequate Work Control practices
  No systematic method of checking system readiness
Contributing Causes:
  Poor communication between System Owners and Operability
    Poor attendance at coordination meetings
    Inadequate tools for communicating/determining status

## Slide 5: How the new HCO system addresses findings
  No systematic method of checking system readiness
  Inadequate documentation of system status/condition before turn-on.
  Tools for System Owners/RECO inefficient or inadequate for information management.
  No LCW valve lineup data/indicators (tags) at magnets.
  LCW flow/cooling effectiveness not verified on the magnets.
  Power supply not fully inspected prior to installation.
  Very light attendance at RECO meetings by System Owners.
  Inadequate documentation of system status/condition before turn-on.
  Undocumented jumper installed in power supply.
  Failure to pass along known problems with power supply identified on Sept 2011
HCO Status Software
HCO Group Checklists
ABIL
HCO Process

## Slide 6: New HCO Approach
Identify the users
Involve everyone
  Engage both technicians and management.
  Involve them in the system design
Get specific
  HCO software captures checkout of each component.
  Ensure work plans are developed for component HCO
Be efficient
  HCO software is web-based
  It efficiently handles documentation.
  Displays multiple, dynamic reports.
Change the culture
  Ensure management actively and visibly supports the process
  Accelerator Readiness Reviews (ARR) helped by ensuring we completed the steps we committed to during the reviews.

## Slide 7: Users
Technicians – Work to checkout components based on HCO requirements.
Group Leaders & Experts – System Experts, Group Leaders, Engineering Liaison work together to determine system readiness.
Management – Program Deputy (PD), Engineering Liaison, and Operability managers monitor/drive HCO progress based on beam destinations.
Operations – Verifies component status based on beam destinations prior to establishing beam for the PD’s accelerator program.

## Slide 8: Determining Component Readiness Status
New process utilizes a three stage sign-off process
  Components are initially “Not Ready”.
  Technicians upgrade them to “Checked” once work is completed
  Group leaders upgrade them to “Ready” once work is reviewed.
Staff can add comments without having to change status.
Anyone can downgrade a component to “Not Ready”.
Once all groups have signed off on a component, the component name will be turned GREEN on the interface.

## Slide 9: Readiness Status
Readiness: status of all accelerator components needed for operations.
  Built from a “superset” of the accelerator’s element database (CED)
Accelerator status:
  Can be filtered and displayed based on beam destination

## Slide 10: HCO Checklists
Checklists are used (and required) for each group performing work that could cause damage to personnel or the machine during beam operations.
HCO Checklists are:
  Maintained by work groups.
  Stored in the HCO database
  Documented using a configuration management process in software.
Checklists improve outcomes with no increase in skill
(A. Gawande, Checklist Manifesto)

## Slide 11: “Bulk” Sign-off
Signoff of components:
  Currently: 8,104 elements, 18,679 signoffs
  One at a time” approach won’t work.
  Solution?
Regional signoff option
  Group leader or technician can verify that all components in the region have been Checked/Ready.
  Allows groups to signoff higher level equipment that supports specific components (i.e., a single bulk power supply that supports ARC 1 dipoles).

## Slide 12
North East Spreader

## Slide 13: Group Signoff
The software interface:
  Is web-browser accessible.
  Shows all associated groups in work order.
  Provides for simple bulk signoff of components.
  Facilitates making, tracking, and reviewing comments.

## Slide 14: Signoff - Filtering

## Slide 15: Overall Status

## Slide 16: Group-by-Group Progress

## Slide 17: Group-by-Group Status Breakdown

## Slide 18: Drill Down

## Slide 19: HCO Process Execution
HCO Program
  HCO team leaders serve as Program Deputy (PD)
    Beam destination set based on program goals
  HCO software filters and displays components that require HCO.
  Group leaders and geographic integrators continually verify that the lists of components are accurate.
Coordination and Sign-off
  Integrated activities coordinated daily 0800 meetings:
    Communicate system status, tunnel access.
    Detail work priorities
    Resolve any group and/or schedule conflicts.

## Slide 20: Accelerator Startup

## Slide 21: Summary & Conclusions
New HCO system ties together people, process, resources, and environment.
  Process developed with system owners involvement.
  HCO components require groups to have a written checklist
  Technicians “Check” components.
  Group leaders responsible for saying components are “Ready”
  HCO software provides web-based status of accelerator readiness

## Slide 22
Thank You!
Questions?